## Slide 1: Project Overview
Flemming Videbaek
Brookhaven National Laboratory

## Slide 2: Overview
Project Overview and scope definition
  High level technical overview
Baseline Project
  Deliverables
  CD-4 Key Performance parameters
  Cost and Schedule, Milestones
  Funding Profile, contingency
Management
  Organization
  Reporting, Tracking and project controls
Risk Management
  Risk Management Plan
  Risk registry
Readiness for CD-2/3
  Design Status

## Slide 3: Detector Overview

## Slide 4: STAR detector
STAR is an existing detector that has operated for 11 years at RHIC.
HFT is an upgrade to the inner tracking system of STAR

## Slide 5
The fine spatial resolution of the tracker will allow direct topological identification of parent particles with very short lifetimes from decays of heavy quarks, such as the D0 and D* meson and the c baryon. In addition, the HFT will allow exclusive and inclusive reconstruction of charm and bottom semileptonic decays.
HFT Definition
TPC – Time Projection Chamber
(main tracking detector in STAR)
HFT – Heavy Flavor Tracker
SSD – Silicon Strip Detector
  r = 22 cm
IST – Inner Silicon Tracker
  r = 14 cm
PXL – Pixel Detector
  r = 2.5, 8 cm
Notes: Revisit text (make sure it does not say – direct top reconstruction of bottom1¡

## Slide 6: Inner Detector Support
MSC
Pixel Insertion Tube
Pixel Support Tube
IDS
East Support Cylinder
Outer Support Cylinder
West Support Cylinder
PIT
PST
ESC
OSC
WSC
Shrouds
Middle Support Cylinder
Inner Detector Support
Carbon Fibre Structures provided support
For 3 inner detector system.
All systems highly integrated into IDS
E.Anderssen LBL mech engineer
D.Beavis, BNL subsystem manager

## Slide 7: Cross section View
Outside inside tracking with graded resolution.
The two inner layers tracking to vertex determines the
requirements to PXL.
50 cm
Beampipe
SSD
IST
Pixel Detector
TPC
SSD
IST
PXL
~1mm
~300µm
~250µm
vertex
<30µm

## Slide 8
PXL Detector Subsystem
Mechanical support with kinematic mounts (insertion side)
Insertion from one side
2 layers
5 sectors / half (10 sectors total)
4 ladders/sector
Aluminum conductor Ladder Flex Cable
Ladder with 10 MAPS sensors (~ 2×2 cm each)
carbon fiber sector tubes (~ 200µm thick)
20 cm
Subsystem manager L. Greiner

## Slide 9: Intermediate Silicon Tracker subsystem
Intermediate tracking layer with good r-phi resolution 250mm
Conventional Si strip detector using CMS APD chip for ladders
Readout system copy of just completed FGT detector system
Subsystem manager Bernd Surrow. Talk by G. v Nieuwenhuizen, MIT
20 50 cm long ladders at 14 cm radius.

## Slide 10: Silicon Strip Detector
The ladders and Si-sensors is an existing detector.
Upgrade readout system with new ladder cards on detector, RDO cards, and cooling system
Subsystem manager: Jim Thomas, LBL
Ladders
Ladder Cards

## Slide 11: Project Chronology
2005 - The Inner vertex tracking upgrade identified as a critical component soon after the start of RHIC and developed into proposal and R&D projects within STAR. Reviewed by BNL Detector Advisory Committee and included in the RHIC detector upgrade mid-term plan.
2007 - Reviewed by BNL Technical Advisory Committee
2008 – pre-CD-0 review
2009 – CD-0 approval
- pre-CD-1 review
2010 – CD-1 approval
Notes: Which brings us to today.

## Slide 12: Baseline project

## Slide 13
HFT consists of 3 sub-detector systems inside the STAR Inner Field Cage (IFC)
  Pixel Detector (PXL) – 2 layers
    Removable detector system with insertion mechanism.
  Intermediate Silicon Tracker (IST) 1 layer
  Silicon Strip Detector (SSD) 1 layer
Detector resides in a Inner Detector Support (IDS) that is integrated with the Forward Gem Tracker (FGT) that will occupy West end of the IFC.
Online software
Not an HFT deliverable but required for integration is a new small diameter beam-pipe (procurement outside project scope)
Not an HFT deliverable, but required for physics analysis is offline software. The development is coordinated by the project
HFT Detector and Deliverables
Notes: Note the 4 systems were described above.

## Slide 14: Performance requirements
High-Level Key Performance Parameters (KPP)
The high-level KPPs cannot be directly measured without beam. The capability to achieve these parameters can be demonstrated at CD-4 through the measurement of the low-level KPPs plus simulation studies using the full STAR detector simulation package and analysis software.

## Slide 15: Low-level CD-4 KPPs
experimentally demonstrated before installation:
The achievement of the low-level KPPs will be proven through bench tests, survey measurements and the meeting of design specifications (Appendix A of PEP)
Will be addressed in sub-system talks
Parameters can be demonstrated and documented before final assembly and installation of HFT in the STAR detector.
Notes: More in sub-system talks

## Slide 16: HFT project deliverables
3 Si detector systems
  PXL sectors, insertion mechanism and spare sectors , sensors and electronics
  IST ladders with si, readout system, and spares
  SSD upgraded electronics, cooling
Global support structures for the 3 detector system integrated into the STAR detector
Online and control software
The details are listed in PEP

## Slide 17: Schedule considerations
PXL detector can be inserted into STAR in one-day, once the small diameter beam-pipe is integrated with IDS
IST and SSD can only be installed during RHIC shutdown periods and requires roll-out of STAR. This period is not always fixed in a given year, but is typically July-November
The 3 subsystems will be fabricated, assembled and tested on their respective support cylinder (PXL/PST), (IST/MSC) and (SSD/OSC). This stage allows for verification of most low level KPPs.
The final assembly of the detector subsystems into the complete HFT instrument will be done when STAR can be rolled out. The project schedule allows one year for this activity, while the EF schedule calls for this in fall of 2013.
Following such assembly 6 months is allocated for final close-out preparations.

## Slide 18: Considerations II
An engineering run with pre-production PXL ladders for run-13.
  The engineering run will assess open issues for the PXL sub-system, and help in retiring project risks ahead of the final assembly.
The Forward Gem Tracker (FGT) is highly integrated with IDS, and imposes constraints on space envelopes for HFT detectors and IDS stability requirements (E.A. talk)

## Slide 19: Summary Schedule

## Slide 20: Level 1 and 2 Milestones
High level (L2)reportable technical milestones in support of CD milestones
The schedule has additional distributed L3 milestones to track each subsystem.
Level | Milestone | Planned | Actual/Forecast
1 | CD-0 Approve Mission Need |  | 2/18/09 (A)
1 | CD-1 Approve Alternative Selection and Cost Range |  | 8/31/10 (A)
1 | CD-2 Approve Performance Baseline | Q4FY11 | Aug-11
1 | CD-3 Approve Start of Fabrication | Q4FY11 | Aug-11
1 | CD-4 Approve Project Completion | Q3FY15 | Jun-15
1.2 | PXL |  | 
2 | PXL Prototype Sector Design Complete |  | 12/15/10 (A)
2 | Receive Prototype sensors from IPHC |  | 3/15/11 (A)
2 | Prototype PXL Insertion mechanism Testing Complete | Q1FY12 | Sep-11
2 | Final PXL Sensors received | Q1FY13 | Oct-12
2 | Production Sector Assembly Start | Q2FY13 | Feb-13
2 | PXL detector available for insertion | Q1FY14 | Jun-13
1.3 | IST |  | 
2 | Sensor design Finished | Q1FY12 | Jul-11
2 | Prototype ladder tested | Q2FY12 | Dec-11
2 | Flex hybrid produced | Q3FY12 | Feb-12
2 | First staves produced | Q4FY12 | Jun-12
2 | Staves finalized | Q2FY13 | Nov-12
2 | IST assembled onto MSC | Q4FY13 | Mar-13
1.4 | SSD |  | 
2 | Prototype Ladder Board design finished |  | 10/15/10 (A)
2 | RDO Prototype Board design finished | Q1FY12 | Jul-11
2 | Preproduction Design Review of RDO | Q3FY12 | May-12
2 | Production of Ladder Boards ready to begin | Q1FY13 | Nov-12
2 | SSD assembled on OSC ready for installation | Q1FY14 | Sep-13
1.5 | Integration |  | 
2 | Production OSC/MSC at BNL for Integration | Q4FY12 | Jun-12
2 | Inner detector support assembled with SSD/IST and FGT | Q1FY14 | Sep-13
2 | HFT Installed and Integrated into STAR | Q1FY15 | Dec-13

## Slide 21: Cost Baseline
Notes: Contingency is

## Slide 22: Funding Profile
Profile as of CD-1, and in PEP
Redirects are included under WBS 1.1

## Slide 23: HFT MIE Cost/Budget Profile
Chart: $M
| 2010.0 | 2011.0 | 2012.0 | 2013.0 | 2014.0
1.0 HFT - MIE | 0.038367 | 2.595 | 8.0503 | 11.3986 | 11.5455
2.0 OPC - R&D | 0.13038 | 0.3 | 0.3 | 0.3 | 0.3
Actuals | 0.27852 | 1.0385
Funding | 2.7 | 5.6 | 10.15 | 14.55 | 15.5
Contingency
Notes: Redirected support thru FY12 is approx. $684K of budget. Less this the expenditures in FY12 are expected to be cumulatively $8,050K
I would zero actual line from FY12 forward

## Slide 24: Management

## Slide 25: HFT Org Chart
1.2
1.3
1.4
1.5
1.6

## Slide 26: HFT management

## Slide 27
1.1 Management
  Management, oversight, ESSH/QA and reporting of the project.
1.2 Pixel detectors – Leo Greiner, LBL
  Howard Wieman, LBL
  Sensors, readout systems and mechanical support, insertion mechanism, services
1.3 IST detector – Bernd Surrow, MIT
  Gerrit van Nieuwenhuizen,LBL
  Sensors, readout system ladder support ,services
1.4 SSD detector – Jim Thomas, LBL
  Michael LeVine, BNL
  Upgrade to the readout electronics of the SSD, and services.
1.5 Integration and Global structures– Dana Beavis, BNL
  Eric Anderssen LBL ( deputy engineer)
  Global support structures, Interfaces to STAR, Safety
1.6 Software – Spiros Margetis, Kent State
  Development and commissioning of Online software
  Coordination of STAR offline effort for HFT (not deliverable)
WBS Organization

## Slide 28: Reporting & Communication
High Level
  Project Assessment and Reporting System (PARS II) updated on a monthly basis by the Federal Project Director (Lloyd Nelson, BNL site office)
  Contractor Project Director provides a monthly report to FPD, a monthly teleconference is held with DOE HQ
  The CPD provides quarterly reports to DOE using inputs from subsystem managers and BNL management, and a quarterly telecon is held
  Annual progress reviews with outside experts will be conducted by DOE (NP)

## Slide 29: Reporting & Communication
Weekly
  Meetings with FPD weekly, or as needed.
  Technical committee (Management issues, progress reports)
  Hardware group meeting (PXL, IST, SSD)
  Integration team (sometimes bi-weekly)
    Members from HFT, FGT projects and STAR operations group.
  Software group
  SSD sub-system (bi-weekly) includes engineering participation from
  Subatech, Nantes.
Bi-monthly project meetings
Monthly
  progress report to Collaboration (STAR management)
As often as needed - Management team will conduct design reviews
and technical progress reviews on a regular basis
Regular telecons - LBNL-IPHC, yearly face-to face meetings

## Slide 30: Institutional Organization
Participate in the fabrication of deliverables for the HFT.
BNL is the lead institution.
Brookhaven National Laboratory | BNL
Institut Pluridisciplinaire Hubert Curien, Strasbourg, France | IPHC
Kent State University | KSU
Laboratory for Nuclear Science, Massachusetts Institute of Technology, Cambridge | MIT-LNS
Lawrence Berkeley National Laboratory | LBL
SUBATECH, Ecole des Mines, Nantes, France | SUB
University of Texas, Austin | UT
Notes: From PEP, distinguish between Prohject Inst. And offline insts.

## Slide 31: MOUs
MOUs between BNL/HFT and the collaborating institutions that provide project deliverables describe the expected efforts of on-project, redirected and scientific labor, summarizing people (names/category) and their anticipated FTE fraction of activity related to tasks at the WBS level 2 or 3.
For LBL and MIT the yearly Statement of Work will detail the required funding, tasks, deliverables, and personnel.
Drafts MOUs available in review documentation
  Subatech (signed January 2010)
  IPHC (signature in progress)
  MIT, LBNL, UT, KSU and BNL STAR group

## Slide 32: Risk Management

## Slide 33: Risk Management
The Risk Management Plan (RMP)
The risk assessment has been performed by subsystem and reviewed with management.
The sub-system manager used the risk matrix to evaluate moderate and high risk project items.
Risk are also reflected in the applied contingency analysis
Risk list is available for reviewers.

## Slide 34: High Risks
A few high level risk for PXL has been retired though early prototyping and tests
  Cooling
  Sensor development
Mechanical risk IDS are becoming low, due to fabrication of WCS(FGT) and ESC prototype.
Most risk are related to schedule, and are at low to moderate impact
Notes: This will be revised

## Slide 35: Documentation Status
Since CD-1 review:
Updated PEP according to DOE order 413.3B
Updated Risk Management Plan, and reviewed risk list
pHAD updated
NEPA determination (categorical exclusion)
Technical Design Report
Responded to DOE CD-1 recommendations
Updated Basis of Estimate
Updated bottom up analysis of Cost & Schedule

## Slide 36: Readiness

## Slide 37: Design Status
Subsystem talks will demonstrate project readiness in detail.
Due to the extensive period of R&D and work since CD-0/CD-1 reviews, the engineering design and prototyping are very advanced, and efforts are turning toward fabrication planning.
This includes pre-production and testing before final fabrication.

## Slide 38: Design Status
Design is well advanced
  Ultimate PXL design and readout large complete
  Design nearly done for PXL mechanics and prototyping for critical insertion mechanism underway for testing in July.
  IST sensor and hybrids design done; prototype ladders to be produced shortly.
  SSD Ladder Board and RDO board progressing well.
  Inner Detector Support design complete

## Slide 39: Design Reviews so far
2011
IST sensor design Review, BNL January 26 sites.google.com/site/istprototypereview/ ; final review report
2010
PXL sensor Review BNL December 6,7 http://rnc.lbl.gov/hft/hardware/docs/sensor_review/index.html
PXL RDO and sensor review at LBL June 23-24. http://rnc.lbl.gov/hft/hardware/docs/elec_review/
Inner Detector Support requirements meetings and review. March and May.
2009
HFT overall design review. March 25-26 BNL

## Slide 40: Summary
Designs and prototyping nearly complete, ready for first fabrication.
Schedule is integrated, costs documented and managed as a whole.
Risks are being addressed and managed, several high level ones have been addressed early.
The Project is ready for CD 2/3

## Slide 41: Backup Slides

## Slide 42: Change Control Thresholds
 | DOE-SC-26 | DOE-SC-26 | DOE-BHSO | HFT
 | Associate Director | Program Manager | Federal Project Director | Contractor Project Director
 | (Level 0) | (Level 1) | (Level 2) | (Level 3)
Scope | Any change affecting Mission Need | Any change affecting CD-4 deliverables | N/A | Any change not affecting CD-4 deliverables
Cost | Any increase in TPC | Any change to TEC or OPC, or cumulative allocation of ≥ $500k contingency | A cumulative increase of ≥ $250k in WBS Level 2 elements, or cumulative allocation of ≥ $250k contingency | Any increase of ≥ $50k in a WBS Level 2 element
Schedule | Any delay in CD-4 date | ≥ 3 months delay of a Level 1 milestone date (other than CD-4), or ≥ 6-month delay of a Level 2 milestone date | ≥ 3-month delay of a Level 2 milestone date | ≥ 1-month delay of a Level 2 milestone date, or ≥ 3-month delay of a Level 3 milestone date

## Slide 43: WBS definition

## Slide 44: Collaboration and Responsibilities
BNL
  Project management, integration, safety, SSD electronic upgrade
LBL
  PXL detector, PXL readout, Global support, SSD, integration, management
MIT
  IST detector
IPHC
  Sensor development
SUBATECH
  Engineering for SSD readout
UT
  PXL readout, PXL telescope beam test
Kent State, UCLA, Purdue, NPI, CTU, USTC
  - Software development as part of calibration, offline needs.
Notes: Should Nantes be on this

## Slide 45: Risk Analysis Matrices

## Slide 46: Labor resources
On-Project labor is defined as the technical and engineering effort associated with R&D, preliminary/final design and engineering, fabrication, and assembly, and project management.
  Scope included in the work breakdown structure
  Cost included in the HFT TPC and is funded within R&D and MIE funds
Redirected labor is associated with design, engineering, fabrication, and assembly efforts and refers to engineers and technicians already funded.
  Decreases the amount of new funds needed to implement the project
  Scope included in the work breakdown structure under 1.1
  Cost included in the HFT TEC, funded by DOE Program
Scientific labor is supporting the overall development and operational capability of the HFT detector within the STAR experiment, including software and physics analysis models.
  Scientific labor cost is not included in the HFT TPC
  Scope integrated with the HFT project schedule

## Slide 47: Schedule Highlights
Each sub-system completes Q4FY13.
Assembly and integration with IDS thereafter, instrument completely assembled during subsequent RHIC shutdown.

## Slide 48
HFT Definition
Notes: Revisit text (make sure it does not say – direct top reconstruction of bottom1¡

## Slide 49: Structures Exploded Detail
MSC
Pixel Insertion Tube
Pixel Support Tube
IDS
East Support Cylinder
Outer Support Cylinder
West Support Cylinder
PIT
PST
ESC
OSC
WSC
Shrouds
Middle Support Cylinder
Inner Detector Support

## Slide 50: Nomenclature
Detectors
PXL pixel subsystem
IST Inner Silicon Tracker
SSD Silicon Strip Detector
Structures
IFC STAR TPC inner field cage
IDS Inner Support Structure
WCS,ESC West and East Cone Structure
OSC Outer Support Cylinder
FGT Forward GEM Tracker (independent upgrade)