## Sheet1
STAR Heavy Flavor Tracker (HFT) DOE Recommendations and Action Items July 13-14 CD2/3 Review
ID No. |  | Recommendation | Required Action (Discussion) | Action Person | Current Status | Expected Date | Additional Information
Technical
1 | rec | •Decide by September 1 which technology, Phase-I or Ultimate Prototype, to implement in the engineering run. However, CD-2/3 approval is not contingent upon this decision. | Provide to HFT management a plan that outlines the difference between the current baseline, and the path with Ultimate. Identify change in cost and man-power, and evaluate risks with this. | Leo, Howard
Mechanics
2 |  | All three HFT subsystems make use of the LBNL composite facility – it is recommended that a series of milestones be incorporated in production schedules in order to keep track of numerous components | Should be developed in connection with the overall list of L3 milestones. See also 12.
3 |  | • A detailed assembly document should be generated for both the pixel and IST ladder construction. Tracking components used in ladder assemblies will become integral to a data base for the detector. | This is a good suggestion. The timeline for doing this is on end of year. It is important to have the prototype assembly tried out before. | Leo, Gerrit |  | 2011-12-31
Safety
4 | rec | 1.Finalize and sign off the Hazard Analysis for the HFT including adding/clarifying language that discusses that the hazards of the HFT are bounded and do not impact the authorization basis or the ASE for the RHIC which the HFT will fall under by CD-2/3. This declaration should be documented using the USI process prior to CD-4. | First item ready for ESAAB eq. | Dana
5 | rec | .Assure buy in from the BHSO NEPA coordinator that the HFT project falls within the bounds of the RHIC Environmental Assessment by 11/1/11 |  | Dana
6 | rec | Prior to CD-4 update the security evaluation to show the project is covered under the most current update to the site assessment. |  | Dana
Management
7 | rec | Evaluate the Critical Path for ambiguities prior to CD-2/3 ESAAB Equivalent | Have generated new chart showing critical path. Due to float on subsystem the de facto critical path (as per project) is the installation only. | Sarah, Flemming |  |  | Sarah will write a short doc with chart and words for discussion
8 | rec | •Evaluate KPPs and Deliverables to determine if they are vital and essential for achieving mission needs prior to CD-2/3 ESAAB-equivalent | Discuss if the approach taken so far is the right one. The deliverables can certainly be simplified. | Flemming, Spiros, Jim, Helmut, Lloyd
9 | rec | •MOUs should be approved prior to CD-2/3 ESAAB-equivalent | Push inst to signoff on the MOU's. | Flemming
10 | rec | •Review the scope of WBS 1.6 prior to CD-2/3 ESAAB-equivalent | There seemed to be two different approaches. A) eliminate or b) expand to cover fundamental task needed for software, but this then also requires pulling all of this together in a short timeframe. This may be difficult. | Flemming. Spiros |  |  | Needs further discussion
11 | rec | •Assess the potential project risk of a FY 2012 Continuing Resolution longer than 3 months prior to CD-2/3 ESAAB-equivalent | Assume risk for project. Continue to develop FY12 funding and spending scenarios , including major preocurements. Indetify consequence of 6mo, 9mo 12 mo CR. Establish alternate mitagation strategies. | Flemming, Sarah + sub-system managers
12 | rec | Consider adding interim milestones to effectively monitor Project performance prior to CD-2/3 ESAAB-equivalent | From the discussion in the management breakout, this was not mean to add additionl L2, but to maintain a project L3, that can be reported in the monthly e.g. by given current and upcoming, not nesc the full list. It should be a version controlled list in e-room. The L3 should be clearly identified in the baseline project file.One issue here is that the project as such is planning on a monthly basis to follow the task in the baseline WBS. What does the FPD and NP lead want to see tracked. See also 2 above. | subsystem, Flemming, Sarah
13 | rec | Recommend seeking SC guidance on how to account for redirected labor and scientific resources on the project that are not MIE funded prior to CD-2/3 ESAAB-equivalent | Contact SC to establish how guidance can be obtained.Lloyd should be lead on this since it goes across projects and even SC offices. | Lloyd, Sarah,Kerry. |  |  | Should thias really possible delay the ESAAB date? That would be unfortunately.
pixel
14 | com | •Testing should continue to assure that the design and technical solutions extend to the full and completed system.
15 | com | •Efforts should continue to better understand the ultimate radiation and background environment at small radius and the impacts on sufficiency of the design in ensuring the success of the HFT in delivering physics. | On background follow-up with Phenix results from run-11. | Identy person to wotk with Phenix
16 | com | •The complete set of KPP don’t define the physics performance of the HFT in the face of uncertain backgrounds. It would be useful to have a simple physics benchmark (not an additional KPP) that can be used to assess the physics impacts resulting from a better understanding of backgrounds and operational challenges.
IST
17 | com | •Given the large number of chips/hybrid, yield and reworkability may be important and the design and production plan should be developed with this in mind.
18 | com | •Initial hybrid prototypes often have issues, and any problems with the prototype hybrid may have schedule impact. There is 5 months of schedule float in the IST. Much of this would be absorbed by a second hybrid run. The project might want to consider mitigation strategies, such as parallel production of prototypes with a second vendor.
SSD
19 | com | •The SSD system refurbishment is, to a significant extent, beyond control of the project. This represents a risk which is difficult to control. This is partially mitigated by the redundant nature of the SSD/IST system.
20 | com | •Tasks such as the redesign of the ladder board and the specification of readout board FPGA pinout are already being paced by availability of engineering at Subatech.
21 | com | •The collaboration might consider adding a KPP to track SSD physics performance goals. | This seems to go against the higher gola of reducing KPP.
22 | com | •The project has proven adept at heading off a potential delay resulting from an error in the layout of a printed circuit board by quickly developing a simplified version of the board at a second institution. This simplified board will serve to avoid schedule slips in the testing of other components
Mechanics
23 | com | •A better understanding on the performance of the HFT cooling systems should be demonstrated as a part of a prototype test run.
24 | com | •If a first IST ladder is available for inclusion in a prototype test run it should be included.
25 | com | •Choreography will be a key element in the installation and operation of the HFT in STAR. There are many other detectors that will become integral to this operation; beam beam counter, East start counter, forward GEM detector, beampipe and bake out.
Safety
26 | com | •Hazards Analysis (HA) Report for the HFT Project Document dated June 2011 is comprehensive and meets the intent of DOE O 413.3B “Program and Project Management for the Acquisition of Capital Assets” that requires a Preliminary Hazards Analysis Report. The HA states that CAD will authorize the safety approval through and Unreviewed Safety Issue (USI) for the RHIC Safety Analysis Document (SAD), and that the HFT does not change the Accelerator Safety Envelope for RHIC. This USI has not been generated at this time nor is the HA finalized/signed. No new hazards were identified and a determination that the HFT hazards are bounded by the existing CAD Safety Assessment Document should be stated in the PHAR. The HA should be re-titled to a Preliminary Hazards Analysis Report so there is no confusion that it meets the 413.3B requirements
27 | com | •A NEPA review was conducted and concluded that the HFT proposed actions fall within the scope of the RHIC Environmental Assessment, DOE EA #0508. The memo dated September 16, 2010 is from the BNL site NEPA coordinator to the CAD Associate Director for ESH and states that the review was coordinated with the BHSO NEPA Coordinator, however a memo from BHSO was not issued.
Cost & Schedule
28 | com | •Cost estimate appears reasonable for achieving KPPs
29 | com | •Cost contingency is $3,655k and appears reasonable
30 | com | MOUs are an essential project resource but 5 of 7 are not approved
31 | com | •Off project activities (FGT and beam-pipe) appear to be appropriately integrated with this HFT project
32 | com | •The Critical Path contains parallel activities that causes ambiguity
Management
33 | com | •It is unusual to have both low and high level KPPs as well as Deliverables
34 | com | •As currently written the low-level and high-level KPPs appear overly complicated