Critical Decision Summary Document

| Site: | Brookhaven National Laboratory | FPD: | name: Lloyd Nelson phone: 631-344-5225 e-mail: lnelson@bnl.gov |
| --- | --- | --- | --- |
| Project Title: | Heavy Flavor Tracker MIE-01VB |  |  |
| Near Term Total Project Cost | $15.2M | Life Cycle Cost | $17.8M |

Site Level Funding Profile

| Funding Scenario | FY 2009 | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | $3.0 | $3.4 | $5.2 | $5.1 | $1.1 |

Critical Decision 2/3 – Approve Performance Baseline

| CD-2/3 Approved | Check only when CD-2/3 is approved. | Notes All requirements for CD 2/3 shall be in accordance with DOE Order 413.3B |
| --- | --- | --- |
| Acquisition Executive Authority Secretary Under Secretary Program Secretarial Officer Program Manager/Field Manager (SES) Date Received: |  | Approval Authority: Gillo, Jehanne E. Director Phone: 301-903-1455 Route Symbol: SC-26.2 Building: GTN Location: GERMANTOWN MD Routing: SC-26.2 Organization: Facilities and Project Management Division Office of Nuclear Physics, Office of Science Title: Director, Facility & Project Management Division Internet Address: jehanne.simon-gillo@science.doe.gov |
| Critical Decision Approval Secretary Under Secretary Program Secretarial Officer Program Manager/Field Manager (SES) Date Received: |  | Approval Authority: Jehanne Gillo, Director Facilities and Project Management Division Office of Nuclear Physics, Office of Science |
| CD – 2/3 REQUIREMENTS |  |  |
| Performance Management Baseline | Completed N/A Date to Complete: | CD 2/3 ESAAB date is tentatively scheduled for March 31, 2011. All ESAAB Documents need to be submitted 2 weeks (March 17, 2011) prior to ESAAB. Final BNL review prior to submittal starts March 4. (Includes final Risk Management Plan) |
| Final Project Execution Plan | Completed N/A Date to Complete | Final PEP shall be revised in accordance with recommended format from November 16 D. Lehman presentation. |
| Earned Value Management System | Completed N/A Date to Complete | BSA/BNL has a DOE approved EVMS. HFT is below $20M threshold requirement. |
| Performance Baseline Validation IPR | Completed N/A Date to Complete | HFT is below $20M threshold requirement. |
| Performance Baseline Validation EIR | Completed N/A Date to Complete | HFT is below $20M threshold requirement. |
| Independent Cost Estimate or Review | Completed N/A Date to Complete | HFT is below $20M threshold requirement. |
| Quality Assurance Program | Completed N/A Date to Complete | BSA/BNL has a DOE approved QAP IAW DOE O 414.1C. Reference Memo stating QAP iaw with SBMS is added to HFT website. |
| Preliminary Design | Completed N/A Date to Complete | Formal Design Review supports performance baseline for all subprojects and is added to HFT website. |
| Update Project Data Sheet | Completed N/A Date to Complete | HFT is an MIE Project |
| Design Review | Completed N/A Date to Complete | A design review was performed for the Conceptual Design Report. Additional reviews will be performed as part of CD-2/3. |
| Safety Design Strategy | Completed N/A Date to Complete | Not a HazCat 1, 2 or 3 nuclear facility |
| Hazard Analysis Report | Completed N/A Date to Complete | The final Hazard Analysis will completed at CD-4, however an updated Preliminary Hazard Analysis Report is required if any new or significant changes are applicable. If no changes a memo stating a review has been completed shall be sufficient and added to HFT website. |
| Update Preliminary Security Vulnerability Assessment Report | Completed N/A Date to Complete | 9/29/09 Report evaluated the HFT Project and determined no changes to the SVAR is required. If no changes a memo stating a review has been completed shall be sufficient and added to website. |
| Preliminary Safety Validation Report | Completed N/A Date to Complete | Not a HazCat 1, 2 or 3 nuclear facility |
| Preliminary Sustainable Environmental Stewardship | Completed N/A Date to Complete | No buildings/facilities involved |
| National Environmental Policy Act Documentation | Completed N/A Date to Complete: | A copy of all NEPA documentation is added to HFT website. |
| Preliminary Documented Safety Analysis Report | Completed N/A Date to Complete | Not a HazCat 1, 2 or 3 nuclear facility |
| Safety Evaluation Report | Completed N/A Date to Complete | Not a HazCat 1, 2 or 3 nuclear facility |
| Construction Project Safety and Health Plan | Completed N/A Date to Complete | Project Safety Health Plan is submitted to DOE for approval. |