HFT - SOFTWARE

Resources

Institutional Responsibilities

Milestones

PRPPRELIMINARY

DRAFT

Version 1.3

July 31, 2026

# Institutional Contributions to Software effort

The tables list the responsibilities and the manpower available for the software tasks connected with the construction and operation of the HFT.  We start with an overview detailing the responsibilities of all institutes and than list the responsibilities and tasks of the individual institutions by year and task.  The manpower listed is sufficient to perform all the tasks listed in the task list.  In addition to this manpower, the STAR collaboration as a whole will be involved in the physics analysis of data derived from the HFT detector as indicated by the “statement form the STAR spokesperson”.

| BNL | Simulations |
| --- | --- |
| IPHC | Simulations Analysis software |
| KSU | Software Coordination Simulations Tracking, calibration and alignment SSD Software |
| LBNL | Simulations Pixel calibration and alignment Test data analysis SSD commissioning |
| MIT | Simulations IST calibration and alignment IST Test data analysis |
| Prague | Simulations Cosmic ray tests |
| Purdue | Simulations Tracking development Calibration and alignment Analyze test data Cosmic ray tests |
| UCLA | Simulations Tracking software |
| USTC | Simulations Analysis software Calibrations |

| Software task |  | BNL | IPHC | UCLA | KSU | NPI | MIT | LBL | Purdue | USTC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Offline |  |  |  |  |  |  |  |  |  |  |
| Hit Reconst. | IST |  |  |  |  |  | X |  |  |  |
|  | Pixel |  |  |  |  |  |  | X | X |  |
| Tracking |  | X | X |  |  |  |  |  |  |  |
| Event Vertex |  | X | X |  | X | X |  |  |  |  |
| Decay Vertex |  | X | X |  | X | X |  |  |  | X |
| Calibration Db | SSD | X |  |  | X |  |  | X |  |  |
|  | IST | X |  |  |  |  | X |  |  |  |
|  | PXL | X |  |  |  |  |  | X | X |  |
| Alignment | SSD | X |  |  | X |  |  | X |  |  |
|  | IST | X |  |  | X |  | X |  |  |  |
|  | PXL | X |  |  | X |  |  | X | X |  |
| Simulation |  |  |  |  |  |  |  |  |  | X |
| Geometry | SSD | X |  |  | X |  |  | X |  |  |
|  | IST | X |  |  |  |  | X |  |  |  |
|  | PXL | X |  |  |  |  |  | X |  |  |
| Fast/Slow Sim. | SSD |  |  |  | X |  |  | X |  |  |
|  | IST |  |  |  | X |  | X |  |  |  |
|  | PXL |  | X |  |  |  |  | X | X |  |
| Embed./Pileup | IST |  |  |  | X |  | X | X | X | X |
| Assoc/Analysis |  | X |  |  | X | X |  |  |  |  |

Detailed Institutional Responsibilities

BNL

| Year | FTE | Need | Name | Task |
| --- | --- | --- | --- | --- |
| 2012 | 0.4 |  | JH.Lee | Simulations |
| 2013 | 0.5 |  | JH.Lee | Simulations |
|  | 0.5 |  | Student | Analysis software |
| 2014 | 0.5 |  | Postdoc | Analysis software |
|  | 0.5 |  | Student | Analysis software |

IPHC Strasbourg

| Year | FTE | Need | Name | Task |
| --- | --- | --- | --- | --- |
| 2012 | 0.5 |  | Postdoc | Analysis software |
|  | 0.5 |  | Student | Simulations |
| 2013 | 0.5 |  | Postdoc | Analysis software |
|  | 0.5 |  | Student | Analysis software |
| 2014 | 0.5 |  | Postdoc | Analysis software |
|  | 0.5 |  | Student | Analysis software |

IPHC will concentrate on B meson physics.

Kent State University

| Year | FTE | Need | Name | Task |
| --- | --- | --- | --- | --- |
| 2011 | 0.25 |  | S. Margetis | Simulations/Alignment/Analysis |
|  | 0.5 |  | Postdoc | Simulations – Analysis – SSD software |
|  | 0.4 |  | Students | Calibration - Tracking - Analysis |
| 2012 | 0.45 |  | S. Margetis | Simulations/Alignment/Analysis |
|  | 1.0 |  | Postdoc | Simulations – Analysis – SSD software |
|  | 1.2 |  | Students | Calibration - Tracking - Analysis |
| 2013 | 0.5 |  | S. Margetis | Simulations/Alignment/Analysis |
|  | 1.0 |  | Postdoc | Simulations – Analysis – SSD software |
|  | 2.0 |  | Students | Calibration - Tracking - Analysis |
| 2014 | 0.5 |  | S. Margetis | Simulations/Alignment/Analysis |
|  | 1.0 |  | Postdoc | Simulations – SSD software |
|  | 2.0 |  | Students | Calibration - Tracking |

KSU is responsible for the overall software design. KSU’s physics analysis will concentrate on the analysis of RCP initially.

LBNL

| Year | FTE | Need | Name | Task |
| --- | --- | --- | --- | --- |
| 2011 | 0.5 |  | Postdoc | Prepare analysis code |
|  | 0.5 |  | Postdoc | Pixel Calibration |
|  | 0.5 |  | Student | Pixel Calibration |
|  | 0.2 |  | E. Sichtermann | Work with Postdoc and Student on simulations and analysis code |
| 2012 | 0.5 |  | Postdoc | Prepare analysis code |
|  | 0.5 |  | Student | Prepare analysis code |
|  | 0.5 |  | Postdoc | Pixel Calibration |
|  | 0.5 |  | Student | Pixel Calibration |
|  | 0.2 |  | E. Sichtermann | Work with Postdoc and Student on simulations and analysis code |
| 2013 | 0.5 |  | H. Wieman | Detector Operator (Pixel) |
|  | 0.3 |  | E. Sichtermann | Work with Postdoc and Student on simulations and analysis code |
|  | 0.5 |  | H. Matis | Detector Operator (SSD) |
|  | 0.5 |  | H.G. Ritter | Work with Postdocs and Students |
|  | 0.5 |  | N. Xu | Work with Postdocs and Students |
|  | 1 |  | Postdoc | Calibration |
|  | 1 |  | Postdoc | Calibration |
|  | 0.5 |  | Student | Calibration |
|  | 0.5 |  | Student | Calibration |
| 2014 | 0.5 |  | H. Wieman | Detector Operator (Pixel) |
|  | 0.5 |  | E. Sichtermann | Work with Postdoc and Student on physics analysis |
|  | 0.5 |  | H. Matis | Detector Operator (SSD) |
|  | 0.5 |  | H.G. Ritter | Work with Postdoc and Student |
|  | 0.5 |  | N. Xu | Physics Analysis |
|  | 1 |  | Postdoc | Calibration |
|  | 0.5 |  | Student | Calibration |

LBNL is responsible for the calibration software of the Pixel detector and for analysis software. LBN also is participating in the SSD upgrade. LBL also will be responsible for the operation of the Pixel and the SSD detector. Initially, LBNL will concentrate on the D0 analysis and extracting v2 for D mesons.

MIT

| Year | FTE | Need | Name | Task |
| --- | --- | --- | --- | --- |
| 2011 | 0.3 |  | G.J van Nieuwenhuizen | IST calibration and alignment |
|  | 0.5 |  | Postdoc | Prepare IST calibration, software |
|  | 0.5 |  | Student | Prepare IST calibration, software |
| 2012 | 0.3 |  | G.J van Nieuwenhuizen | IST calibration, alignment, analysis |
|  | 0.5 |  | Postdoc | Analyze cosmic ray tests |
|  | 0.5 |  | Postdoc | Prepare physics analysis code |
|  | 0.5 |  | Student | Slow Controls |
|  | 0.5 |  | Student | Alignment |
| 2013 | 0.3 |  | B. Surrow | Work with Students |
|  | 0.6 |  | G.J van Nieuwenhuizen | IST Detector operation, calibration, analysis |
|  | 0.5 |  | Postdoc | Physics Analysis |
|  | 0.5 |  | Postdoc | Detector operation |
| 2014 | 0.3 |  | B. Surrow | Work with Students |
|  | 0.6 |  | G.J van Nieuwenhuizen | IST Detector operation, calibration, analysis |

The MIT group will deliver and maintain the IST detector software, including slow controls, calibration software and detector specific software. This will be achieved by a phased approach with the software development closely following the detector development. The MIT physics program focuses on the study of heavy quarks in proton-proton collisions at a center-of-mass energy of 200GeV and 500GeV. Here, the main objective is the cross-section measurement of heavy quark production. In addition, the MIT group is planning to use the IST and SSD to aid the charge sign discrimination for mid-rapidity W production in the electron/positron decay mode at a center-of-mass energy of 500GeV in proton-proton collisions.

NPI ASCR/CTU Prague

| Year | FTE | Need | Name | Task |
| --- | --- | --- | --- | --- |
| 2011 | 0.5 |  | Student | Prepare analysis code |
|  | 0.5 |  | Student | Cosmic ray tests |
|  | 0.3 |  | J. Bielcik | Cosmic ray tests |
| 2012 | 0.5 |  | V. Kouchpil |  |
|  | 0.5 |  | Student |  |
| 2013 | 0.5 |  | V. Kouchpil |  |
|  | 0.5 |  | Student |  |
|  | 0.3 |  | M. Sumbera | Work with students and post-doc |
| 2014 | 0.5 |  | V. Kouchpil |  |
|  | 0.5 |  | Student |  |
|  | 0.3 |  | M. Sumbera | Work with students and post-doc |

The Prague group will initially concentrate on developing the analysis tools and analyzing the C.

Purdue University

| Year | FTE | Need | Name | Task |
| --- | --- | --- | --- | --- |
| 2011 | 0.5 |  | W. Xie | Work with Student and Postdoc on HFT calibration and data analysis. |
|  | 1.0 |  | Postdoc | HFT Calibration software development Tracker/Vertex finders development |
|  | 0.5 |  | Student | Tracker/Vertex finders development |
|  | 0.5 |  | Student | Tracker/Vertex finders development |
| 2012 | 0.5 |  | W. Xie | Work with Students and Postdoc on data analysis and reconstruction software development |
|  | 0.15 |  | Fuqiang Wang | Work with Students and Postdoc |
|  | 1.0 |  | Postdoc | Development of reconstruction software for physics |
|  | 0.5 |  | Student | Tracker/Vertex finders development, analysis code development |
|  | 0.5 |  | Student | Develop data analysis codes |
| 2013 | 0.5 |  | W. Xie | Work with Student and Postdoc analysis software development |
|  | 0.25 |  | Fuqiang Wang | Work with Student and Postdoc |
|  | 0.10 |  | Andy Hirsh | Work with Student and Postdoc |
|  | 1.0 |  | Postdoc | Analyzing cosmic ray test of fully integrated HFT system Analyze data from Pixel detector Analysis software development |
|  | 0.5 |  | Student | Analysis software development Analyzing cosmic ray test of fully integrated HFT system |
|  | 0.5 |  | Student | Analysis software development Analyzing cosmic ray test of fully integrated HFT system |
|  | 0.5 |  | Student | Analysis software development |
| 2014 | 0.5 |  | W. Xie | Work with Student and Postdoc and analysis software development |
|  | 0.25 |  | Fuqiang Wang | Work with Student and Postdoc |
|  | 0.10 |  | Andy Hirsh | Work with Student and Postdoc |
|  | 1.0 |  | Postdoc | Detector Operator (Pixel) Analysis software development |
|  | 0.5 |  | Student | Analysis software development |
|  | 0.5 |  | Student | Analysis software development |
|  | 0.5 |  | Student | Analysis software development |

Purdue University will focus on simulations and software development, e.g. the slow simulator. We will also participate in the calibration effort. For the data analysis we will develop the tools for charm and bottom separation and concentrate on this analysis.

UCLA

| Year | FTE | Need | Name | Task |
| --- | --- | --- | --- | --- |
| 2011 | 0.1 |  | H Huang | HFT Physics |
|  | 0.3 |  | G Wang | Physics Simulation/Analysis code development |
|  | 0.5 |  | Student | Physics Simulation/Analysis code development |
| 2012 | 0.2 |  | H Huang |  |
|  | 0.4 |  | G Wang | Tracking Software |
|  | 0.5 |  | Student | Tracking Software |
|  | 0.5 |  | Student | Tracking Software |
| 2013 | 0.2 |  | H Huang |  |
|  | 0.5 |  | G Wang |  |
|  | 0.5 |  | Student |  |
|  | 0.5 |  | Student |  |
| 2014 | 0.2 |  | H Huang |  |
|  | 0.5 |  | Post-doc |  |
|  | 0.5 |  | Student |  |
|  | 0.5 |  | Student |  |

The heavy quark physics in nucleus-nucleus collisions is one of the research topics that the UCLA group will focus on in the coming years. Our involvement in the HFT project will begin with physics simulations related to the detector performance, in particular about the measurement of B and D decay contributions to non-photonic electrons at high transverse momentum. We will also devote graduate Student to analyze open charm production from hadronic decays. Our post-doc and graduate Students will work on analysis software and evaluation of tracking using HFT in the coming years.

USTC Hefei

| Year | FTE | Need | Name | Task |
| --- | --- | --- | --- | --- |
| 2011 | 0.5 |  | Student | Simulations, analysis software |
| 2012 | 0.5 |  | Postdoc | Analysis software |
|  | 0.5 |  | Student | Simulations, Analysis software |
| 2013 | 0.5 |  | Postdoc | Analysis software |
|  | 0.5 |  | Student | Analysis software |
|  | 0.5 |  | Sun Yongjie | Work with Postdocs and Students on preparation of physics analysis |
| 2014 | 0.5 |  | Postdoc | Analysis software |
|  | 0.5 |  | Student | Analysis software |
|  | 0.5 |  | Sun Yongjie | Work with Postdocs and Students |

The University of Science and Technology of China would participate mainly in the work related with HFT/pixel, including calibration/software development,  cosmic ray test and data analysis. As for physics topics, we are interested in measuring charm production cross section, and the separation of charm and bottom production.

# Software Milestones

The milestones in this document are research milestones that are derived from a technically feasible project time line.  We will update those milestones, as the project time line will be refined, especially by including a realistic funding profile.

The research milestones are based on the following project milestones:

TBD

TBD…