WBS 1.6 (Software): Schedule (Template)

# 1.6 Software

#### ID	    		Task-name    		Duration2,3    	Begin-Date      	Predecessors        		Resources

%-Person/FTE

#### 1.6.1 		Hit Reconstruction		30 months		09/01/2011						300/2.0(0.8)

1.6.1.1		PIXEL Hit Reconstruction	30 months		09/01/2011						150/1.1(0.5)

1.6.1.1.1		Develop/Test			8(4) months		09/01/2011		1.6.7.1				100/0.8(0.4)

1.6.1.1.2		Evaluate/Tune		6(2) months		09/01/2011		1.6.7.1				50/0.3(0.1)

1.6.1.2		IST Hit Reconstruction	30 months		09/01/2011						50/0.3(0.1)

1.6.1.2.1		Develop/Test	/Eval.		6(2) months		09/01/2012		1.6.7.2				50/0.3(0.1)

1.6.1.3		SSD Hit Reconstruction	30 months		09/01/2011						100/0.6(0.2)

1.6.1.3.1		Update/Test/Eval.		6(2) months		09/01/2012		1.6.7.3				50/0.3(0.1)

1.6.1.3.1		R&D/Eval.			6(2) months		09/01/2012		1.6.7.3				50/0.3(0.1)

#### ID	    		Task-name    		Duration      	Begin-Date      	Predecessors        		Resources

%-Person/FTE

#### 1.6.2 		Tracking			36 months		09/01/2011						300/3.0(1.0)

1.6.2.1		Update/Test/Evaluate	12(6) months		09/01/2011		1.6.8/1.6.7.1-3		200/2.0(0.5)

1.6.2.2		Alternative Track. Eval.	12(6) months		06/01/2011		1.6.8/1.6.7.1-3		100/1.0(0.5)

#### 1.6.3 		Event Vertex Reconstr.	36 months		09/01/2011						300/2.0(1.5)

1.6.3.1		Au-Au Event Reconstr.	12(6) months		06/01/2011		1.6.2.1/1.6.2.2		100/1.0(0.5)

1.6.3.2		p-p Event Reconstr.		6(6) months		06/01/2011		1.6.2.1/1.6.2.2		100/0.5(0.5)

1.6.3.3		R&D 				6(6) months		03/01/2010		1.6.2.1/1.6.2.2		100/0.5(0.5)

#### 1.6.4 		Decay Vertex Reconstr.	36 months		09/01/2011						200/1.5(0.5)

1.6.4.1		Fitter Dev./Test/Eval.	18 months		03/01/2010		1.6.8/1.6.7.1-3		200/1.5(0.5)

#### 1.6.5 		Calibration/Alignment	36 months		09/01/2010						500/4.7(2.0)

1.6.5.1		SURVEY			15(7) months		09/01/2011						190/2.3(1.1)

1.6.5.1.1		PIXEL Survey			7(3) months		09/01/2011						190/1.1(0.5)

1.6.5.1.2		IST Survey			4(2) months		09/01/2011						190/0.6(0.3)

1.6.5.1.3		SSD Survey			4(2) months		09/01/2011						190/0.6(0.3)

1.6.5.2		GLOBAL Alignment		13(6) months		09/01/2011		1.6.2/1.6.3			100/1.3(0.6)

1.6.5.2.1		PIXEL Global Align.		7(4) months		09/01/2011						100/0.7(0.4)

#### ID	    		Task-name    		Duration      	Begin-Date      	Predecessors        		Resources

%-Person/FTE

1.6.5.2.2		IST Global Align.		3(1) months		09/01/2011						100/0.3(0.1)

1.6.5.2.3		SSD Global Align.		3(1) months		09/01/2011						100/0.3(0.1)

1.6.5.3		SELF Alignment		9(4) months		09/01/2011		1.6.2.1/1.6.2.2		100/0.8(0.2)

1.6.5.3		Test/Verify     		3(2) months		09/01/2011		1.6.2.1/1.6.2.2		100/0.3(0.1)

#### 1.6.6 		Database/HFT Geometry	36 months		09/01/2010						300/1.1(0.4)

1.6.6.1		PIXEL Geometry		6(3) months		09/01/2011						100/0.3(0.1)

1.6.6.2		IST Geometry	     		6(3) months		09/01/2011						100/0.5(0.2)

1.6.6.3		SSD Geometry 		3(2) months		09/01/2011						100/0.3(0.1)

#### 1.6.7 		Response Simulators		36 months		09/01/2010						200/0.8(0.3)

1.6.7.2		IST Simulators	     	6(3) months		09/01/2011						100/0.5(0.2)

1.6.7.3		SSD Simulators		3(2) months		09/01/2011						100/0.3(0.1)

#### 1.6.8 		Embedding/Assoc.		36 months		09/01/2011 		1.6.6/1.6.7			100/0.5(0.2)

Resources

#### ID	    	Task-name    		Institutions			Name			% of time (max)		Years

1.6.1.1	PIXEL Hit Reconstruction	 LBNL, IPHC, Purdue		Postdoc-1		40(60)				3

Student-1		20(40)				3

1.6.1.2	IST Hit Reconstruction	 MIT				Postdoc/Stud.	20(40)				2

1.6.1.3	SSD Hit Reconstruction	 KSU, BNL			Postdoc/Stud.	20(30)				2

1.6.2.1	Tracking Update		BNL, KSU		 	Postdoc/Stud.	30(40)				3

1.6.2.2	Alternative Tracking		BNL, ??			Postdoc/Stud.	10(20)				2

1.6.3.1	Au-Au Vertex Reconstr.	BNL, KSU,??		 	Postdoc/Stud.	20(30)				3

1.6.3.2	p-p Vertex Reconstr.		BNL, ??		 	Postdoc/Stud.	10(20)				3

1.6.3.3	R&D 				BNL, KSU, ??		 	Postdoc/Stud.	10(20)				3

1.6.4.1	Secondary Vertex Rec.	BNL, KSU, ??		 	Postdoc/Stud.	50(70)				3

1.6.5.1	SURVEY			LBNL, MIT, KSU, BNL 	Postdoc+Stud.	2x30(40)			3

1.6.5.2	GLOBAL Alignment		LBNL, MIT, KSU, BNL 	Postdoc+Stud.	2x20(30)			3

#### ID	    	Task-name    		Institutions			Name			% of time (max)		Years

1.6.5.3	SELF Alignment		LBNL, MIT, Purdue, BNL 	Postdoc/Stud.	50(60)				2

#### 1.6.6 	Database/HFT Geometry	LBNL, MIT, KSU, BNL 	Postdoc/Stud.	2x50(70)			3

1.6.7.2	IST Simulators	     	MIT				Postdoc/Stud.	30(40)				3

1.6.7.3	SSD Simulators		LBNL, KSU, BNL		Postdoc/Stud.	20(30)				2

1.6.8 	Embedding/Assoc.		???				Postdoc/Stud.	20(30)				3

See detailed breakdown in Appendix

Top level duration of a task refers to time span it is needed to be done

Sub-level duration refers to actual time needed to complete the task

The estimated effort doesn’t include possible/major infrastructure changes.

The effort for PIXEL response simulator is included in the Hit Finder task. We did not account efforts for possible very-slow simulator development.