## Slide 1: PXL Electronics
Status update for HFT TC meeting on May 11, 2010 at LBNL

## Slide 2: Outline
FY10 Tasks
Status of Tasks
Schedule

## Slide 3: PXL Milestones
Plan “B”
2010-Q1 – Phase-2 sensors delivered to LBNL.
2011-Q2 – Receive prototype final sensor.
2012-Q2 – Install prototype detector at STAR.
2012-Q4 – Receive production sensors.
2013-Q4 – Install PXL detector.

## Slide 4: FY10 Tasks
PXL Cable development
  Infrastructure testing board
  Prototype detector cable FR-4 with Cu
  Prototype detector cable Kapton with Cu
Probe Testing
  Phase-2 sensors
RDO prototyping
  Full ladder RDO
Sensor and system development and testing
  Beam test with Phase-2 @ Fermilab
  Beam test preparation for Phase-2 sector at PHENIX?
CD-2/3
http://rnc.lbl.gov/hft/hardware/docs/Group_Tasks_and_timeline_2010_01_25.pdf

## Slide 5: Probe testing Status
We have a probe testing hardware design and testing plan here http://rnc.lbl.gov/hft/hardware/docs/Phase1/Probe_Testing_Phase1.pdf
We have developed a sensor tracking and QA plan here http://rnc.lbl.gov/hft/hardware/docs/Phase1/sensor_tracking_proposal.doc
We have designed and produced a probe card and mated it to a probe testing station

## Slide 6: Probe testing Status
We have tested 13 sensors (full thickness, individual diced sensors). Up to 3 probe tests per sensor.
Results are very promising with caveats (next slide).
Evaluation in progress
  Mount first 3 tested sensors onto individual test boards. Test for function. – Results look mostly consistent for one sensor with some variation.
  Interface a known good sensor on an individual test board to the probe card inputs. Check probe card function. – Also consistent.
Automated scripts for testing are working.
We will begin testing thinned sensors within the next 2 weeks.
2nd Probe card has been sent out to have the probes mounted.

## Slide 7: Probe testing Status
Poor vs better probe contacts (chip E8)
Initial testing with ~75um travel past touchdown
30 um additional lowering of probe pins
Very Preliminary with known problems

## Slide 8: PXL Cable Development Status
There is extensive documentation of our cable development and testing plan. A report was sent to DOE on 12/31/2009 as part of the CD-1 homework. http://rnc.lbl.gov/hft/hardware/docs/PXL_flex_cable_and_sys_test_v2.doc.
Summary
  Develop FR-4 based infrastructure test PCB. - DONE
  Design FR-4 version of prototype real-size ladder PCB.
  Translate design into Kapton PCB.
This effort requires successful probe testing of sensors in order to be able to test full ladders of functional (Phase-2) sensors.
This is actually a ladder level system test. The testing includes a complete chain of RDO system that has never been fully tested including the prototype MTB and prototype RDO Board. The full ladder signal paths are now being tested.

## Slide 9: Ladder Test System
RDO motherboard
Xilinx V-5 Dev Board
MTB
LU-protected power daughtercard
Infrastructure test board
RDO PC

## Slide 10: PXL Cable Development Status (ladder level system test)
Infrastructure Testing Board
Status:
1 Board loaded with 10 Phase-2 sensors.
JTAG daisy chain working – we can configure and read back.
Multi-drop LVDS clock working @ 160 MHz.
Scripted testing is now working for individual sensors on the ladder.
To do:
Troubleshoot system.
Test individual sensor baseline.
Test with all sensors clocked.
Analyze results.
Repeat for different configurations.
http://rnc.lbl.gov/hft/hardware/docs/Phase1/SCHEMATIC1%20_%20PH1_infrastructure_test_board.pdf
http://rnc.lbl.gov/hft/hardware/docs/Phase1/PHASE-1_INFRASTRUCTURE_TEST.DSN

## Slide 11: Preliminary Testing Results
Probe tests vs ladder tests (chip C1)
Probe tests
ITB
Very Preliminary with known problems
Notes: Vref2 and biases are identical

## Slide 12: PXL Cable Development Status (ladder level system test)
The complete data and configuration paths appear to be working.
We have the firmware/software tools to troubleshoot both the infrastructure testing board and the probe testing systems.
This work has begun – we will fix the existing problems and move to full infrastructure testing of sensor ladders.

## Slide 13: PXL Cable Development Status
Cable design options
A detailed description of the challenge is available here http://rnc.lbl.gov/hft/hardware/docs/PXL_RDO_cable_options_1.doc
We are attempting a “proof-of-principle” test before the CD-2/3 review.
A single sided test cable design has been produced for fabrication at Datex to assess capability and quality. (quotation not yet received)
Some delay due to material issues. It is difficult to find anyone willing to fabricate kapton/Al.
We have located some 1 mil Al on 1 mil mylar and shipped it to Datex. They are evaluating the suitability.
Datex will start first attempt at fabrication next week. Results will follow.
Other vendors (SE SRTIIE, Kharkov,Ukraine and CERN?) will be contacted.

## Slide 14: RDO Prototyping Status
Prototype MTB and RDO boards are fabricated and under test in ladder system test.
Architecture and Implementation documents are in progress due to be completed within 2 weeks.
Full sector RDO (4 ladders) in data taking mode is in progress.
Internal workshop/review is scheduled for June 23-24 2010 at LBNL.
Development of slow control and monitoring system to integrated after internal review.
Effort for beam testing firmware and software is underway.

## Slide 15: Sensor and system development and testing status
Beam test at Fermilab
Measure efficiency of Phase-2 sensors using a sensor telescope.
http://rnc.lbl.gov/hft/hardware/docs/Phase1/Phase-1_telescope_proposal.pdf

## Slide 16: Sensor and system development and testing status
Beam test at Fermilab
We have a draft telescope design (see previous link) and test plan.
Plan uses existing Phase-2 individual testing board design, existing prototype MTB and RDO boards.
  New testing boards have been ordered
  50 um Phase-2 sensors will be delivered in 1 week.
  Design for individual testing board modification is complete.
Initial contact with test beam facility at Fermilab.
To do:
Join with the FGT effort? Depends on schedule.
Write and submit test beam proposal.
Develop firmware for beam test of 4 sensor telescope.
Develop light box and mechanical support structure.
Fabricate trigger detectors (if required)

## Slide 17: Sensor and system development and testing status
Beam Test at PHENIX
Test a full sector of Phase-2 prototype sensors with a full prototype readout path at PHENIX with the new low radius beam pipe.
This would be a very significant test if it can be arranged.
This requires:
Hardware design to integrate with PHENIX.
Coordination with PHENIX for space, electronics space, power, etc.
Successful cable design and fabrication (kapton with Cu traces) – Critical Path.
Completion of all sector RDO firmware and software.
Full validation of assembly fixturing and tools.
Testing and QA hardware, firmware and software for fabrication stages.
No schedule delays

## Slide 18: Schedule (from TC 3/11/2010)
PXL Cable development
  Infrastructure testing board – testing complete May-w4
  Prototype detector cable FR-4 with Cu – testing complete July-w4
  Prototype detector cable Kapton with Cu – testing complete October-w4
Probe Testing
  Phase-2 sensors – batch probe testing thinned sensors working May-w2
RDO prototyping
  Full ladder RDO – documentation complete and internal review May-w1
Sensor and system development and testing
  Beam test with Phase-2 @ Fermilab – TBD, hopefully August-September
  Beam test preparation for Phase-2 sector at PHENIX? - TBD
CD-2/3 – TBD, more information after this meeting?

## Slide 19: CD-2/3
Needed
List of the full set of documentation required for CD-2/3 and schedule for the production of these documents. - DONE
Understanding of mechanism for producing additional required cost and schedule documentation, maintenance and updates.
Institutional reporting requirements and path for fulfilling.
STAR liaisons and infrastructure and design sign-off authority structure.
Sarah will give a presentation on our cost and scheduling efforts for Pixel.

## Slide 20
backup

## Slide 21: Probe testing Status
We need to probe test quantities (~50) of Phase-2 sensors for assembly onto prototype cables to assess the cable design.
This will serve as the development path for the sensor tracking, handling and QA for the main production testing.
We will be testing diced and thinned sensors. This is not usual practice for probe testing (usually wafers) and presents mechanical and handling challenges. HW will present progress on vacuum chuck design for automated production.
Firmware and software for automated testing is complete and under test.

## Slide 22: Sensor / RDO Services (preliminary)
240 W
180W
300W
1350W (AC)
1100W (AC)
Ladders
MTB
Platform
(racks)
RDO
Crate
DAQ
Room
4800 × 42 AWG (TP)
160 × 24 AWG (TP)
40 × 0.42” dia. (50 TP cable)
20 × 16 AWG
10 × fiber optic cable pair
10 × USB
2 × TCD (10 TP)
28 × 12 AWG
2m
6m
~100m
PP
~30m

## Slide 23: PXL Cable Development Status
3 identified Cable design options
Double sided Aluminum conductor with vias
Single sided Aluminum conductor without vias

## Slide 24: Chip A1 individual test (crop this image to show only left upper corner)

## Slide 25: Chip A1 probe test results (crop this image to show only left upper corner)

## Slide 26: Chip A1 individual tests (black) vs probe test results (red)
Notes: Bottom plots –
Mean of upper right on the lower right plot . Histogram on the y axis
Lower left histogram of the sigma of the fit for each transfer function

## Slide 27: Poor vs better probe contacts (chip E8)
Notes: 30 um additional lowering of probe pins
40 columns each drop

## Slide 28: Probe tests vs ladder tests (chip C1)
Probe tests
ITB
Notes: Vref2 and biases are identical

## Slide 29: Probe tests vs ladder tests (chip D9)
Probe tests
ITB
Notes: Vref2 and biases are identical