## Slide 1: HFT Overview
Flemming Videbæk
BNL

## Slide 2: Overview
Selected Highlights (likely to be shown in other talks)
RHIC news
Schedules
Financial Status
OPA review & Other meetings
Issues

## Slide 3: PXL
RDO board designed , produced.
Insertion rail moving ahead

## Slide 4: SSD
Nantes Engineers working on Ladder board design changes
RDO board design and layout well underway.
Software in slow control making good progress

## Slide 5: IST
Prototype ladders populated with chips and APV
Testing going well. Cosmic ray observed.

## Slide 6: Software
Significant work of detailed Geant Geometry, and the BigFatChain (BFC.C).
CCM and database efforts gearing up
FGT
PIXEL
PST
PIT

## Slide 7: RHIC News
Running Schedule
DOE FY13, 14 guidance
  Combine 13/14 into 20 week run
BNL response
  Plan of 15 week run-13.
  Vigdor still want to keep the Dec 1 cool down day
Upcoming BNL management changes important to RHIC and HFT.
  ALD, Physics Dept Chair.

## Slide 8: High level consequence
Assume a run 13/14 would have to start in Sept, STAR roll-in must start ~ July 10.
Neither IST not SSD can be installed.
Even the PXL schedule would get close.
Until this becomes de facto plans I will resist spending much effort from everyone on looking at alternatives (take efforts away from actual work)
If time we can talk about this at end of day.

## Slide 9: Summer Schedule
June 10 Review of status of readiness for installation, ahead of decision to roll-out (from HFT point of view)
June 18 roll out effort begins ..The
July 16 Rollout complete
July 17-20 disassemble IDS
July-21- Aug 4 load test Reassemble IDS Load Test may not be needed.
Aug 6- August 19 Assembly of IDS including WSC with FGT with PST and Be-beam pipe
  The current assembly plan worked out by Eric requires this to be done on floor. For PXL only installation cleanness requirements are modest
2 weeks of schedule contingency.
Sept. 4 IDS lifted/rigger to platform
This requires lifting assembled IDS to SVT platform. Critical lift. WC is still pushing assembly on SVT platform.
Sept 7 STAR roll in starts
Following roll-in (Oct 15?)
  Platform installation
  Beam pipe connections, Bake out
Notes: Taken from our document

## Slide 10: Financial Status
Details by Sarah
High level as per last month
  We have spend k$ 3,178 ( k$385 redirect)
  We have used k$150 of contingency (efficiency on PXL, increase on integration and IST)
  Remaining contingency k$ 3,514
    This is a healthy 35% of cost to complete.

## Slide 11: Issues
Preparations for summer/fall installation.
Collaborator integration into IST efforts (UIC) (positive issues)
Sub-contracts awards. Continue to be diligent.
  MIT 2. installment in place (5 weeks after receiving)
  Indiana (IST/SSD) has taken longer but is in process..
Work on all awards for rest of year
Continue to properly signoff on design and preproduction reviews (internal)

## Slide 12: Open Action Items
Ladder Assembly Plan; IST (CD)
Grounding plan completion; SSD IST (CD)
Initial Safety reviews; IST,SSD
IST cooling liquid
Beam pipe structure
Assembly planning
Notes: comments

## Slide 13: OPA review
Scheduled for July 17-18
Schedule a dry run for June (Date is not easy to identify. PAC 7-8, RHIC users meeting 12-15,STAR upgrade. Possible date: June5/6 or June 18/19
Final rehearsal and polish of talk 1-2 days ahead of the meeting.
More from Lloyd following talk.
Need a schedule overhaul as the one we just completed done so it is appropriately up to date for the dry run and documentation. (Early June absolute deadline)

## Slide 14: Other upcoming meetings
Mid-April ½ day EVO meeting
May F2f at BNL
  UIC people should be available
Heavy Flavor Meeting UIC June 17-18
  http://www2.uic.edu/~kkaude2/hfworkshop2012/

## Slide 15: Summary
There is much progress, and technically it is very promising.
Schedules are tight as has always been known.
Once the assembly schedule for IST is revisited, and the SSD production we will get a much better handle ahead of the OPA review.