## Slide 1: HFT face-2-face
F.Videbaek
Brookhaven National Lab.

## Slide 2: Overview
Meeting Goals
Project Formal Status
KPPs and transition to Operation
Other CD2/3 review recommendation
Technical Status
Tomorrows discussion points

## Slide 3: Meeting Goals
Technical progress since review
High level goals per system through January
  We have the scheduled but like your assessment
Sub system
  Critical items to move forward
  Manpower needs
  Risk, problems
Plans for run-13 and run-14
Heading off DOE requirement up front
  Verification
  Schedule slips
DAQ, slow control discussion
Software efforts ( has to ramp up).

## Slide 4: Project Status
CD2/3 review on July 13-14 at BNL
  Review went very well
  A number of recommendation had to be fulfilled ahead of ESAAB approval meeting
KPP and PEP getting finalized
ESAAB scheduled for October 11 at 11 am

## Slide 5: KPP discussion
At the review GR brought up for the first time the issue of beam verification. This clearly got hold within ONP, even though OPA strongly discouraged this.
This stand prevented the PEP to be finalized and a very large effort have gone into this issue from HFT, BNL HENP and also DOE.
This in end caused delay even though we as project had all documentation ready in time.
Outcome (though not approved given next slide). Not ideal but something we just have to live with- from scientific point of view not bad, but add lots of risk and dependences.

## Slide 6: KPP text
The capability of the HFT system to achieve the KPPs will be demonstrated through the measurement of subsystem functional parameters and detailed, realistic simulations using the full STAR detector simulation package and analysis software. The subsystem functional parameters will be obtained through bench tests, survey measurements, and the meeting of design specifications. The planned early finish schedule has the HFT system ready for installation into STAR approximately two months prior to the Run-14 start date (approximately December 2013). As verification of KPP's with beam is preferred, the project will attempt to demonstrate these using RHIC Run-14 Au-Au collision data.
Notes: There has been many iterations on this

## Slide 7: Primary CD-2/3 recommendation
MOUs were reviewed by ONP in July. Part of research vs. instrumentation resource division discussions and delegation within ONP.
WBS 1.6 was revisited to include CMM, Database software.
Added milestones at L3. These will be tracked by project monthly; also reported monthly to DOE. (Early Finish dates)
ESS&H points completed.
Evaluation of FY12 Continuing resolution (CR)

## Slide 8: Secondary Recommendation & Comments
Select technology for engineering run. Done- Ultimate
Coordination of CF activities via L3.
Generate assembly documentation for PXL and IST ladders.
Continue effrorst to understand radiation environmebt.
IST internal hybrid prototype often have issue. Look at mitigation strategies.!
Be sure other STAR detector components that are integral to integration is consideraed carefully. (BBC, FGT).

## Slide 9: Transition to operation
Message from HM
In addition, we want to modify the approach to the post-CD-4 effort that is needed to turn the HFT into a fully-performing physics instrument, i.e., the effort that is needed to bring the HFT system to optimal performance with beam. We would like BNL to start developing a detailed, project-like plan to achieve this in a timely way, which should include (the equivalent of) a resource-loaded WBS, milestones, and deliverables. This plan would not be a prerequisite to CD-2/3 approval. We will give you further guidance on this in the near future.
These suggestions was also brought up at the June S&T review, and will be
This is clearly a charge to STAR, BNL and the HFT project. It needs to be presented at CD-4 closeout.
It has been discussed with BNL management and also iterated with Helmut as late as last week.
It is still not determined from ONP what they really want.
The PEP will now contain a stetement that such plan needs to be developed.

## Slide 10: Funding
For FY10,11 received 2,300 2,900
Received an additional 1,500k$ in Sept. from FY12 funds (as far I understand).
Total on BNL books 6,800 (~40% total of all funds)

## Slide 11: My view of sub-system status
PXL
  Readout, sensor, test well underway
  PXL Insertion test is about ready; slipped compared to schedule (months)
IST
  Prototype sensor (Hamamatsu) on track
  Ladder prototype test hampered by hybrid cable issues
  SOW needs to be done ASAP
SSD
  Ladder Cards and readout well underway.
  Watching the Nantes connection (sub-contracts delay and hurdles).

## Slide 12: Integration & Global Structures
IDS basically completed for run-12 installation.
There has been some slippage due to extra work, and rechecks. Installation for run-12 on track
Has affected some other activities.
The run-13 open activities (beampipe, NEG coating, heating blankets, MSC) needs attention.

## Slide 13: Carbon Fiber activities
Carbon fiber workshop has multiple activities.
  Global structures
    PST, MSC
  PXL sensors
    Ladder Sectors
  IST
    IST ladders, hybrid cable
  SSD
    Supporting structures
Coordination of these activities is important, and creates linkage between sub-system work.

## Slide 14: Other Activities
Sub-system safety review
  PXL had first yesterday
  Plan for these early so as few surprises as possible late
  Interlock
Slow Control development
  Discussion with STAR S&C
  Interface early also with Creighton Group; may have student available soon to provide interface.
Software must be ramped up.

## Slide 15: Management
Track L3 milestones and cost with sub-systems. Use this as a tool to identify slippage early and follow up on this.
Track cost and progress in WBS monthly.
Continue the good work in documenting our progress in monthly reports.

## Slide 16: Tomorrows discussion points
Address issue brought up by sub-systems
Review the point have have brought up.

## Slide 17: Summary
Thanks to many efforts we are getting funded; many technical issues have been resolved.
Need to keep up the good work and coordinate efforts.
Hopefully the management task will be less since review
The time line is short, let us work to make sure this becomes a success for STAR and the physics program.