## Slide 1: HFT Software Status
S. Margetis, KSU
HF Workshop, June 17, 2012, UIC

## Slide 2
    Schedule/timeline - Milestones
    Manpower update
    General Update
      Activities
      Activities for next calendar year
Dates that drive the priorities/schedule are:
  PIXEL prototype installation next Fall (2012) for Run-13
    2-4 PXL re-configurable sectors
    NO SSD/IST
  Full HFT installation in Fall-2013 for Run-14 data taking
Outline

## Slide 3: Task Overview and FTE needs
2
0.2
1
1.1
FTEY
0.2
0.5
2
0.8
0.5
Total= 8.3
List is for Offline tasks only
FTE estimates do not include BNL-core group contributed effort in tracking/vertex-ing/calibrations etc.
Numbers are on the under-estimate side
It comes down to about 4 FTE/year for ~two years
  We have about half of that

## Slide 4: Schedule/Milestones
NOW
10/2012
10/2013

## Slide 5
LEVEL-3 Milestones
Survey/Alignment/Db/Online are immediate on-project activities
Geometry/Offline/Analysis should be there too

## Slide 6: Areas of activities since CD2/3 (a year ago)
  HFT Geometry model
  HFT Survey & Alignment related work
  Slow/Fast PXL response simulation
  Prototype (BUR) simulations/tracking
  Offline structures (Hits etc)
  Simulation environment (UPC e- background, Pileup)
  Conventions (naming scheme defined), Db
  ----------------------------------------------------------------
  Hit/Event vertex finders/Kalman fitter for decays
  Evaluation/Analysis framework (see Jonathan’s talk)
  Tests of new STV tracker, VMC environment
  ‘Online’ data format/slow controls/online QA/Db considerations
RED = On-scope activity

## Slide 7
HFT Geometry model update
  Creating the Y2013 [a/b] geometry in AgML based on Solid-Works Models
  We had an internal review in March, working on recommendations etc
  Work on SSD/IST in progress
  Work on details of support structures etc in progress
  Manpower probably O.K. but help is more than welcomed (no skills)

## Slide 8: PXL sector modeling in GEANT - detailed work on structure and thickness - optimization in progress

## Slide 10
HFT Survey work
  PXL+SSD work has already begun
    Single chip and 3-chip ladder done. Full PXL sector (photo) ready to go
    SSD ladder preliminary survey done
    IST preliminary work on prototype ladder about to begin at BNL
  We had an internal review on procedures/general scheme in May
  A lot of detailed work in front of us, but expertise is building up
  Manpower issue addressed but there are tasks available

## Slide 11: Sensor’s features for individual pixel coordinates identified - Need be programmable

## Slide 12
SSD

## Slide 13
Slow/Fast PXL response simulation
  Most work done by IPHC (Strasburg) people
  The have developed a Root program, DIGMAPS, for response studies
  Analyzed CERN test-beam data with our sensors to fix parameters
  We are about to get their tune to use for our studies and compare with default “geometrical mean” approach. Then, build fast simulator with appropriate errors.
  SSD exists, IST is relatively simple (but still not there yet)
  Need people to actively pursue these tasks

## Slide 14
Tracking (Physics?) with TPC+PXL prototype ?
  BUR simulations done and presented (Hao/Jonathan)
  Simulations show (see next slide too) that there are physics opportunities but reality might be different
  This connects to the bigger issue of Tracking and whether inside-out tracking is possible. Is CA useful ? We work in that direction.
  This is vital work for the project. ANY help and idea is invaluable.

## Slide 15: BUR (Hao) results based on full simulations

## Slide 16
StPixelFastSimMaker/
StEvent containing PIXEL and IST Hits hits
GEANT
StiPixel
StiIst
Hit
reconstruction
Tracking
StEvent containing tracks
with PIXEL and IST Hits hits
Offline chain
Need to establish working chain
Modify structures/makers to our needs
Closely tied to S&C territory, one needs to be careful
Need to stay informed on new strategies (e.g. no minimc need etc)
We ‘ve gone through initial loops but far from being done (see 2 slides)
Expert help invaluable

## Slide 17
StPixelFastSimMaker/
StEvent containing PIXEL and IST Hits hits
GEANT
StiPixel
StiIst
Hit reconstruction
Tracking
StEvent containing tracks
with PIXEL and IST Hits hits
StIstFastSimMaker/
StDaqMaker/
StDaqLib/
StPixelDaqMaker/
StPixelRecoMaker/
StIstRecoMaker/
REAL DATA STREAM
SIMULATION DATA STREAM

## Slide 18
StEvent
StRndHitCollection
StRndHit
StEvent
StHftHitCollection
StHftHit
Actual structures
Proposed structures
A unique PIXEL/IST hit structure and hit collection
No sub collection (LayerHitCollection, SectorHitCollection) because it is redundant :
  Make the hits collection isSortable() to retrieve the hits the way we want.

## Slide 19
Numbering convention for detector elements
  We have defined and documented the scheme for all HFT elements
  Complies with STAR conventions
  IST example is shown below
http://drupal.star.bnl.gov/STAR/event/2012/03/09/hft-software/hft-numbering-schemedoc-10

## Slide 20: Miscellaneous
  Simulation environment (UPC e- background, Pileup mechanism)
    We did improve our understanding and way of generating this
    We still need to put all this to work with STAR’s official pileup scheme
  Event vertex finders
    Important evaluation work goes on now
  Web Docs
    Jonathan and I are organizing better our Off-Drupal personal doc areas
    Jerome provided an afs area for Off-Drupal (really public) access
    Drupal pages need rework from scratch

## Slide 21: Still to do
  Besides things I have already mentioned above
  Raw data unpackers/Cluster-Hit finders
  Tests of new STV tracker, VMC environment
  ‘Online’ data format/slow controls/online QA/Db considerations
  Make sure we are ready when data starts flowing

## Slide 22
NEEDS
UPDATE
X
UIC
X

## Slide 23: Summary
  In my opinion we are just warming up as a group
  Most of the work is still ahead of us
  Many and diverse areas need attention, work, people