## Slide 1: HFT Software Update
S. Margetis, KSU
S&C, October 26, 2011, BNL
CERN Test beam picture
10K triggers – single chip

## Slide 2: Outline
Task overview and schedule
Progress and expected progress for next year(s)
Issues

## Slide 3: Instead of an Introduction
HFT Software team effort so far concentrated on Physics simulations, CD 0-1-2/3
  This is over as of about now
  Physics performance/simulation work moved to HF forum
The Geometry model/response simulators/tracking/analysis were primitive in those simulations but…τhe regular chain was used, not shortcuts
Effort now is aiming at ~Day-1 operational software
  Online/offline
Dates that drive the priorities/schedule are
  PIXEL prototype installation in Fall-2012 for Run-13
    2-3 PXL re-configurable sectors
    NO SSD/IST
  Full HFT installation in Fall-2013 for Run-14 data taking

## Slide 4: Some clarifications
HFT Software includes both Online and Offline effort
  So far we concentrated on offline tasks/schedule
  Online is to be delivered by ‘hardware’ teams but we need to clarify the situation very soon.
  Online includes: slow controls, data delivery to DAQ, Shift-QA
“Bad DOE experience” with SVT, divided software (artificially) in two categories:
  On-project-scope software activities. Part of PEP. Managed/monitored by HFT-TC and report to DOE. Includes Online, Survey (calibration and alignment)
  The rest. Monitored (internally) by HFT-TC. Includes Geometry, Response simulators, Hit finders, Tracking, Vertexing, Evaluation, track alignment

## Slide 5: WBS task dictionary and schedule has been developed

## Slide 6: Task Overview and Institutions (not uptodate)
2
2
2
1.1
FTEY (50% error)
2
1.5
4.7
0.8
0.5
Total= 16.6

## Slide 7: On-scope Schedule
NOW

## Slide 8: Prioritized list of Tasks for next year
CMM measurements + related work for PXL fixture and sectors
Familiar with one CMM machine at LBL
Scheduled some measurements in the new VIEW-3000 machine
We are on schedule but it is getting tight
  Review in April 2012

## Slide 9: Prioritized list of Tasks for next year
HFT Geometry model update
    Create Y2013a/b geometries
    Jason created ‘blank’ based on Y2012
    We are gathering info on material for Y2013
      What, how much X0
    On schedule but manpower an issue

## Slide 10: Prioritized list of Tasks for next year
‘Online’ data format/slow controls/online QA/Db considerations
  Needs to be defined/clarified a.s.a.p.

## Slide 11: Prioritized list of Tasks for next year
  Slow/Fast PXL response simulation
    Initial work done earlier by Purdue
    Initiated contact with IPHC experts during the HFT Software day (9/2011)
    Got their DIGMAPS code
    Will collaborate to make an acceptably fast ‘slow’ simulator for the chain
CERN Test beam picture
10K triggers – single chip

## Slide 13: Prioritized list of Tasks for next year
Tracking with TPC+PXL prototype?
  Can we do anything substantial here?
    Any physics with the prototype?
  Jonathan spends some time on this right now

## Slide 14: OtherTasks
For the next 2 years
  -------------------
  Evaluation/Analysis framework
  -------------------
  Tests/evaluation of new STV tracker
  Hit reconstruction software
  Event vertex finder evaluation

## Slide 15: Summary
With CD-x behind us we have established contact with STAR S&C group at the HFT Software day, end of last month
  I am here as a result of that contact
We expect an increasing interaction with the BNL-core group
  Started with Jason on geometry but will expand to all areas
We are getting our act (and manpower) together