## Sheet1
STAR Heavy Flavor Tracker (HFT) DOE Recommendations and Action Items March 28-19 BNL read team Review
ID No. |  | Recommendation | Required Action (Discussion) | Action Person | Current Status | Expected Date | Additional Information
Scientific Significance and Merit | Priority
1 |  | The response to CD-1 physics questions should be improved. In particular, strengthen the physics case for heavy flavor measurements in heavy ion collisions at RHIC in 2015 taking into account anticipated progress at RHIC with PHENIX upgrades and at the LHC. |  |  |  |  | Discussion sems to indicate that this is not meant to update the report, but rather have a good presentation focusing on this at the review.
Possibly revisit TDR chapter.
technical status | priority for review
1 | low | Radiation dose effects such as SEU and long term dose effects (e.g. on sensors, front ends, commercial devices, optics and FPGAs) should be tabulated for all sensors/boards along with estimates of rates at the various HFT locations and lists of tests results to date and, if needed, any planned mitigation strategies. | Good suggestion. Could be included in the TDR. Information of rad exists in several places. Collecting it would be good.
2 | low | • Investigate whether the cooling fluid chosen for the IST is sufficiently radiation hard – presumably its a fluorocarbon compound and some can make hydrofluoric acid under radiation damage – not a good thing. |  | GvN,BS |  |  | The issue most likely an issue is that of water in the system (HW), This fluid is being used by ATLAS; should review how that op is handled- Watercooling is an alternate backup solution.
Management
1 | high | Strengthen and formalize the communications between the STAR collaboration and the project. Interface issues, priority, scheduling should be discussed and agreed formally in that forum. (If it exists it was not visible in the presentations.) | Establish regular meeting beteen HFT INT and STAR Managamernt+OPS (Beavis, Christie, Dunlop,Videbaek)
2 | high | Strengthen and formalize the communications and reporting lines between the project integration functions and the experiment. | as above |  |  |  | What is means by experiment here- STAR ops is not experiment
3 | high | The project management needs to be strengthened with a part time Mechanical Engineer and a part time Electronics Engineer | Have part time el eng involved in coordinating and documentation activities. Take hand of doc, grounding, cable routing, participate in review |  |  |  | The 4/18 meeting with TL,EoB SV made it clear that the EA role is ok
4 | high | The integration role should be strengthen and include among other issues: envelopes, location of services, detailed routing of services, grounding rules etc.
5 | high | The project needs to show that they have established engineering design and documentation standards that all subsystems must follow. This should be integrated with STAR Operations documentation requirements. A common database has been established where all project documents need to reside and can be accessed by the project and STAR. Decide on drawing standards, number system, ECR/ECN, work controls, technical note and procedure formats to be followed. The project needs to develop an internal mechanism for identifying, documenting and resolving engineering change control issues. | Documentation standrad for (final drawings, and change control will be worked out with CC.d'Agistino, and set as standard for project, in particur,. See also 3electric, | FV, Ciro d'Agistino after consultation with J.Dunlop
6 | high | There needs to be a plan for detector installation presented based on delivery of components and STAR detector configuration and operation. The project needs to demonstrate mechanical techniques required for component assembly, installation, access, logistics, support in STAR, and support of the vacuum beam pipe. There needs to be better communication of project integration and installation requirements with STAR Operations. | This (Technical part) I believe was resolved after presentation of E.Andersen; Most of this is in assembly document, design document. EA as mech eng has the lead role here. The later part is addressed by the
7 | recommendation | Safety reviews and reporting lines should be visible on the org. chart and known to all subsystem managers. |  |  |  |  | How can a safety review by on an org chart?
8 | recommendation | Change control – the role of BNL oversight management should be clarified and visible on the change control chart | Not clear what is meant here
9 | high | Draft MOUs should be discussed with DOE NP ASAP. There is no need to wait for a final draft. |  | FV+institutions
10 | high | CD4 deliverables should be defined as clearly as possible. The CD-4 deliverables should be clearly achievable on the time line promised. | Revisit, clarify and rewrite | JT,Spiros and FV | In progress | Draft by 4/25- citculate to project group before discussion with DOE.
11 | high | The collaboration should prepare in an easily accessible format (like a book) the following information: WBS, WBS dictionary, Cost Book, schedule and a short overview of the scope of the project with a few transparencies and tables. (Enough so that a reviewer can check to see if the cost estimate is right). |  | FV,S.Morgan |  |  | The use of ATLAS/LBNE is being looked into.
12 | high | Contingency should be assigned to the individual items with possibly a much smaller general contingency to take into account currency fluctuations, foreign contributions and other contributions that are not assured by DOE. | agree- |  |  |  | This addresses the large 'unknown-unknown issue. Impliers revisiting sub-systems and cont evaluation
13 | recommendation | Employ a uniform Risk analysis
14 | recommendation | The schedule should show Key milestones with dates | In presentation ? Not in PEP
15 | recommendation | The presentation of the “redirected” funds is confusing. Suggest it is treated separately – and just mentioned that it will be tracked by the project. |  |  |  |  | This needs to be discussed with helmut. Afterall it was agreed upon with DOE, and if they are satisfied why should it be changed.
16 | medium | A clear statement of the objectives of the 2012-13 Pixel engineering run should be made. | A write-up will be completed, and included in overall presentation | L.Greiner
17 | recommendation | Needed resolution should be stated in the three dimensions: Z, R-Phi, and R. We assume the stated resolution is in R-Phi and that the other dimensions are significantly larger. | Revisit, clarify and rewrite | JT,Spiros and FV | 3 meetings, and draft document being prepared for sub-system managers.
19 | recommendation | Defne and agree what are the requirements for 1. Placements | Revisit, clarify and rewrite, see above. | JT,Spiros and FV
2. Accuracy on a ladder –
a. ladder relative a neighboring ladder on the cylinder
b. Placement of the cylinder in the experiment
c. Survey accuracy – how well do you need to know the locations before the beam?
3. Stability – over what period of time?
4. How well do you need to know the locations for tracking?
5. Any calibration and/or active monitoring systems?