## Slide 1: SSD Tasks and Costs
Howard Matis
October 14, 2010

## Slide 2: Boundary Conditions
Tasks are 85% complete
Schedule is about 30% done – lots of guesses
Cost not done
Work done by a novice physicist – Not by an engineer
  Estimates of time has been optimistic in the past

## Slide 3: WBS Structure
1.4.1 Mechanics
1.4.2 Electronics
1.4.3 Assembly
1.4.4 Infrastructure

## Slide 4: 1.4.1 Mechanics
Needed now
Needs to be done during OSC design

## Slide 5: Mechanics - Comments
Need envelope of ladder cable board soon
Most of mechanical work can be done in 3 months
Do we need to design brackets before OSC design is finished?
  Must put in those constraints
Engineering support for WBS
When will this be done
SSD Mounting brackets needed before alignment

## Slide 6: 1.4.2 - Electronics
Ladder Board
  Prototype
  Preproduction
  Production
Ladder Board
  Prototype
  Preproduction
  Production
DAQ
  Prototype
  Production
Integrated Test System

## Slide 7: Assumptions
Preproduction does not start until have tested RDO and Ladder Board
Modification
Preproduction
Modification if necessary
Production

## Slide 8: Ladder - 1
Done
The next big thing to do is test!!!

## Slide 9: Ladder-2

## Slide 10: Ladder-3

## Slide 11: RDO
Critical Items

## Slide 12: FPGA Progress
FPGAs critical to success of project
FPGAs for VME and DAQ/Trigger
  VME design mostly done
  DAQ/Trigger big question
    Needs SUBATECH resources
    Have not received a date when this will be completed
  Need pinouts for RDO Board development
Slave FPGA well underway by Micheal
RDO board needed to test Ladder Board

## Slide 13: DAQ
At least one TCD high priority

## Slide 14: DAQ Comments
Using conventional DAQ for STAR
Minimal technical risk
Resources for this is minimal
Tonko will do much of it
Nevertheless, we need to develop diagnostic software

## Slide 15: Test System

## Slide 16: Test Comments
Need to purchase minimal elements of power supply soon
  As soon as we confirm power requirements of Ladder Board
Slow controls needed soon
Decide how many systems we need
Do we need TCD and how soon can we get it?

## Slide 17: 1.4.3 - Assembly

## Slide 18: Assembly Comments
Where to do testing?
  LBNL – requires extra airplane flight
  BNL – can alignment be done there
Need to mount carbon elements to SSD ladders
  LBNL shop can do that
  Can BNL do it?
Who will do the translation from measurements to STAR database?

## Slide 19: Infrastructure – 1.4.4
Cables 1.4.4.1
  Relatively easy to produce
  Some risk in aluminum cables
    Should start now
  Need to have concept of patch panels on OFC and ESC
  Pick power supply soon so that can develop slow controls
    Wiener is a good choice
  Need to start cooling
    Jim is coming back
  Slow controls big manpower gap
    Get hardware
    Need person soon (within a year)

## Slide 20: Summary
Current end date is 5/1/14
Assuming perfect funding and manpower
Funding
  We are using R&D funding
  Need funds at LBNL
  Project funds
We are physicist limited
  Need Slow Controls assistance
  Also alignment
Engineering support
  Develop cost
Some engineering needed today
How to do commissioning?
SUBATECH is not forever
  No physicist on project
  New director – not from our field
  Need resources to complete their contribution
Funding transfer to LBNL