## Slide 1: HFT project Overview and Status October 14, 2010
F.Videbaek
BNL

## Slide 2: Meeting Structure
Organization
  Today: talks by sub-system
    Cost and Schedule
    Changes in scope since cd-1\
    Identify uncertainties (risk, contingencies)
    Identify schedule drivers
    Walk through schedule at some detailed level (5) – i.e. major steps
    Manpower available for sub-system. Resource conflicts
    Plans/activities - reviews
    Technical Brief progress report
  Afternoon
    Talks as needed – Discussion on base-lining and near term plan with solid deadlines.
    Monthly telecon 4pm/ tour to IR
    Continued discussion
  Friday
    Coordination via e-room
    Continued discussion.

## Slide 3: Overview This talk
Progress since Last meeting
  CD-1 approval; homework
  Funding status, cost status
Schedule for CD-2/3
  Concerns In view of August/Sept progress
Base-lining and sub-system WBS coordination
  High-level considerations
  Assessment of status
Reporting
  Monthly, quarterly, milestone status
Requisites for CD 2/3
  documents

## Slide 4: CD-1 Approval follow-up items
The CD-1 review was on August 31, 2010
Minutes from ESAAB review
Jehanne Gillo also made the following suggestions to the Program Manager and FPD to be considered prior to CD-2:
  Ensure that all recommendations resulting from prior reviews have been appropriately responded too and that there is general agreement by all parties.
  Revise the Project Execution Plan (PEP) to be a more concise document—the preliminary PEP is still too detailed.
The ESAAB Equivalent Board unanimously recommended approval of CD-1, and Jehanne Gillo signed the decision documentation.

## Slide 5: Funding Status
Have k$2,400 at BNL
SOW for LBL work through Feb has been signed; funds transferred (k$940)
SOW for MIT being developed.
BNL cost fairly small for that period, up to base-lining.
Keep contingency and management reserve at BNL
September Monthly expenditure

## Slide 6: Near Term HFT Schedule
Our baseline plan from July was based on
  Mid October (now) had first schedule in hand and iterated once combined
  Early Dec – Vigdor/BNL review
  Early Feb or Mid March DOE CD2/3 review
  At earliest CD2/3 approval end March
As of today we are not far enough to schedule the Nov meeting. Progress today and in coming two weeks will determine if this is feasible.
My estimate we are 2-3 weeks behind where we wanted to be

## Slide 7: Base-lining and sub-system coordination
High-level considerations
  I: Have PXL+SSD | IST in place for run-14 i.e simmer 2013
  II: Optimize STAR installation got summer 2011 ie. run-13 with WCS(FGT) , proto OSC and ESC
  III: Summer 2012 may be far enough to have new BeamPipe and MSC structure. A run-12 PXK eng run may be possible, but is not in the baseline plan
  Minimize STAR openings
  There are clearly other intermediate desirable goals but the high-level goals are important.

## Slide 8: Assessments of Status (Tuesday)
PXL
  Electric: schedule and cost in WBS. Tasks cost rolled up from cost book
  Mechanical: cost book cost, manpower done; schedule from before, but not filled, durations?
IST
  Schedule (CD-1) and cost in WBS; Contingency analysis performed. Not adjusted to current time frame
SSD
  Task list and dependencies in WBS. No cost and contingency analysis performed.
Integration
  Status as PXL, Mechanical; Needs handover to Dana for installation scheduling.
Management
  Not done, but relatively simple. Allocating project people, and meeting/review schedules
No dependencies across sub-systems.
No sure cost books will come out in uniform way. Needs reporting tools to pull this of WBS.
BOE –costbooks, other documentation.

## Slide 9: Reporting
Monthly Reports
  At end of month send reminder to tc-list; expect to receive ahead of 2 Thursday (telecon) 5 business days; Report to finalize around the 20’th of each month.
  After this months report we have gotten into a good mode for these. A few corrective suggestions
    Please supply in word
    When referring to people give full name.
    Identify acronyms first time. Will build up a standard glossary at end.
    Monthly report goes to Lloyd Nellson BHSO, and with copy to Helmut Marsiske. The content is essentially reported at monthly telecon.

## Slide 10: Quarterly report
High level report for Federal Project Director (FPD) to DOE HQ. Also associated with telecon.
Usually needs to be complete on ~ 20 on the month following the end of quarter.
Kerry have a draft based on model from EBIS. See next two slides on likely content.
Needs financial input/summary; descriptive part will be based on previous 3 months report.

## Slide 13: Documents for CD-2/3
  Performance baseline (WBS,COSTbooks, BOE)
  Final Design (TDR + supporting documents)
  Updated risk assessment registry
  Updated PEP
  Updated Hazard Analysis
  NEPA document (DONE)
  Updated Q&A program
Need to incorporate the completion of these into our near term plans.

## Slide 14: Conclusions
Many open ended issues; goal for this meeting to set specific near term goals so we can meet a good cd2/3 schedule and the ultimate run-14 installation.
The need for scheduling vs. design and technical progress has to be kept in mind.