## Baseline Milestones
| current date |  |  | 2011-09-26
| watch date |  |  | 2011-10-30
Level | Milestone | PEP Date | Date | Planned | Actual | Forecast | Note |  | Level | Milestone | Planned | Actual /Forecast
1 | CD-0 Approve Mission Need | Q2, FY09 (A) | Feb-09 (A) |  | 2009-02-18 |  |  |  | 1 | CD-0 Approve Mission Need | Q2, FY09 (A) | 2/18/09 (A)
1 | CD-1 Approve Alternative Selection and Cost Range | Q4, FY10 (A) | Aug-10 (A) |  | 2010-08-31 |  |  |  | 1 | CD-1 Approve Alternative Selection and Cost Range | Q4, FY10 (A) | 8/31/10 (A)
1 | CD-2 Approve Performance Baseline | Q4FY11 | 2011-10-11 | 2011-08-01 |  | 2011-10-11 |  |  | 1 | CD-2 Approve Performance Baseline | Q4FY11 | 2011-10-11
1 | CD-3 Approve Start of Fabrication | Q4FY11 | 2011-10-11 | 2011-08-01 |  | 2011-10-11 |  |  | 1 | CD-3 Approve Start of Fabrication | Q4FY11 | 2011-10-11
1 | CD-4 Approve Project Completion | Q3FY15 | 2015-06-01 | 2015-06-01 |  | 2015-06-01 |  |  | 1 | CD-4 Approve Project Completion | Q3FY15 | 2015-06-01
2 | PXL Prototype Sector Design Complete | Q1FY11(A) | Dec-10 (A) |  | 2010-12-15 |  |  |  | 2 | PXL Prototype Sector Design Complete | Q1FY11(A) | 12/15/10 (A)
2 | PXL Receive Prototype sensors from IPHC | Q2FY11(A) | Mar-11 (A) |  | 2011-03-15 |  |  |  | 2 | PXL Receive Prototype sensors from IPHC | Q2FY11(A) | 3/15/11 (A)
2 | PXL Prototype PXL Insertion mechanism Testing Complete | Q1FY12 | 2011-12-01 | 2011-09-27 |  | 2011-11-15 | delayed: due to IDS production, and occupancey of tooling. Currently being assembled. |  | 2 | PXL Prototype PXL Insertion mechanism Testing Complete | Q1FY12 | 2011-11-15
2 | PXL Final PXL Sensors received | Q1FY13 | 2012-12-01 | 2012-10-16 |  | 2012-10-16 |  |  | 2 | PXL Final PXL Sensors received | Q1FY13 | 2012-10-16
2 | PXL Production Sector Assembly Start | Q2FY13 | 2013-03-01 | 2013-02-15 |  | 2013-02-15 |  |  | 2 | PXL Production Sector Assembly Start | Q2FY13 | 2013-02-15
2 | PXL detector available for insertion | Q1FY14 | 2013-12-01 | 2013-06-25 |  | 2013-06-25 |  |  | 2 | PXL detector available for insertion | Q1FY14 | 2013-06-25
2 | IST Sensor design finished | Q1FY12(A) | Jul-11 (A) | 2011-07-11 | 2011-07-08 |  | Final drawings resubmit to hamamatsu |  | 2 | IST Sensor design finished | Q1FY12(A) | 7/8/11 (A)
2 | IST Prototype ladder tested | Q2FY12 | 2012-03-01 | 2011-12-11 |  | 2012-01-23 |  |  | 2 | IST Prototype ladder tested | Q2FY12 | 2012-01-23
2 | IST Flex hybrid produced | Q3FY12 | 2012-06-01 | 2012-02-20 |  | 2012-04-03 |  |  | 2 | IST Flex hybrid produced | Q3FY12 | 2012-04-03
2 | IST First staves produced | Q4FY12 | 2012-09-01 | 2012-06-27 |  | 2012-08-09 |  |  | 2 | IST First staves produced | Q4FY12 | 2012-08-09
2 | IST Staves finalized | Q2FY13 | 2013-03-01 | 2012-11-02 |  | 2012-12-18 |  |  | 2 | IST Staves finalized | Q2FY13 | 2012-12-18
2 | IST assembled onto MSC | Q4FY13 | 2013-09-01 | 2013-02-01 |  | 2013-03-18 |  |  | 2 | IST assembled onto MSC | Q4FY13 | 2013-03-18
2 | SSD Prototype Ladder Board design finished | Q1FY11(A) | Oct-10 (A) |  | 2010-10-15 |  |  |  | 2 | SSD Prototype Ladder Board design finished | Q1FY11(A) | 10/15/10 (A)
2 | SSD QRDO Board design finished | Q1FY12 | Jul-11 (A) | 2011-07-11 | 2011-07-05 |  |  |  | 2 | SSD QRDO Board design finished | Q1FY12 | 7/5/11 (A)
2 | SSD Preproduction Design Review of RDO | Q3FY12 | 2012-06-01 | 2012-05-30 |  | 2012-07-13 |  |  | 2 | SSD Preproduction Design Review of RDO | Q3FY12 | 2012-07-13
2 | SSD Production of Ladder Boards ready to begin | Q1FY13 | 2012-12-01 | 2012-11-29 |  | 2012-11-06 |  |  | 2 | SSD Production of Ladder Boards ready to begin | Q1FY13 | 2012-11-06
2 | SSD Assembled onto OSC ready for installation | Q1FY14 | 2013-12-01 | 2013-08-29 |  | 2013-08-28 |  |  | 2 | SSD Assembled onto OSC ready for installation | Q1FY14 | 2013-08-28
2 | IGS Final MSC assembled at BNL | Q2FY13 | 2013-03-01 | 2012-11-05 |  | 2012-11-05 |  |  | 2 | IGS Final MSC assembled at BNL | Q2FY13 | 2012-11-05
2 | IGS Final OSC at BNL | Q4FY13 | 2013-09-01 | 2013-05-19 |  | 2013-05-19 |  |  | 2 | IGS Final OSC at BNL | Q4FY13 | 2013-05-19
2 | IGS HFT assembled and integrated into STAR | Q1FY15 | 2014-12-01 | 2013-11-20 |  | 2013-11-20 |  |  | 2 | IGS HFT assembled and integrated into STAR | Q1FY15 | 2013-11-20
| L3 EF mileston | EF date | Forecast
PXL | L3 - sector laminates ordered | 2011-09-09 | ? | 2011-09-09 |  | 2011-10-31 | I like to change that one.
| L3 - Production Ladders Ready for Sector Mounting | 2013-02-14 | 2013-02-14 | 2013-02-14
| L3 - 1st production sectors ready | 2013-04-15 | 2013-04-15 | 2013-04-15
| L3 - Insertion Test bed complete | 2011-06-27 | 2011-10-30 | 2011-06-27 |  | 2011-11-23 | delayed: due to IDS production, and occupancey of tooling. Currently being assembled.
| L3 - Kinematic Mount prototyping complete | 2011-08-15 | 2011-11-30 | 2011-08-15 |  | 2011-11-23 | delayed: due to IDS production, and occupancey of tooling. Currently being assembled. New estimate by JS
| L3 - Cart Fabrication 1st unit complete | 2012-03-19 | 2012-03-19 | 2012-03-19
| L3 - Patch Panel Bulkhead 1st unit complete | 2012-04-18 | 2012-04-18 | 2012-04-18
| L3 - PXL final sensor order | 2012-08-13 | 2012-08-13 | 2012-08-13
| L3 - Infrastructure test ladder board readout and analysis complete |  | 6/20/11(A) |  | 2011-06-20 |  | Draft report released 6/30/2011
| L3 - Prototype Kapton/Cu Cable 1st prototype complete | 2012-03-06 | 2012-03-06 | 2012-03-06
| L3 - Prototype Kapton/Al Cable 1st prototype complete | 2012-08-01 | 2012-08-01 | 2012-08-01
| L3 - Full RDO of ladder (ITB) prototype |  | 6/20/11(A) |  | 2011-06-20
| L3 - V6 based RDO MB 1st prototype tested | 2012-03-21 | 2012-03-21 | 2012-03-21
| L3 - V6 RDO motherboard - 1st production prototype complete | 2012-11-01 | 2012-11-01 | 2012-11-01
| L3 - First Production Ladders Ready for Sector Fabrication | 2013-02-13 | 2013-02-13 | 2013-02-13
| L3 - Deliver 2nd Detector + Spare Ladders | 2013-09-27 | 2013-09-27 | 2013-09-27
IST | L3 CP - Prototype flex hybrid produced | 2011-07-12 | 10/8/11(A) | 2011-07-12 |  | 2011-10-12 | First two fabs failed (august delivery)
| L3 CP - Prototype sensors produced | 2011-09-19 | 2011-12-15 | 2011-09-19 |  | 2011-12-15 | Hamamatsu extended del by 1 mo due to supplier issues. Drawings submitted on time. Hamamatsu just announced a two month deleivry slip due to equipment problems.
| L3 CP - Support structure produced | 2012-01-25 | 2012-01-25 | 2012-01-25 |  | 2012-01-25
| L3 CP - Transition boxes produced and tested | 2012-03-19 | 2012-03-19 | 2012-03-19 |  | 2012-03-29
| L3 CP - Start wire bonding readout chips | 2012-04-04 | 2012-04-04 | 2012-04-04 |  | 2012-05-16
| L3 CP - Sensor procurement finished | 2012-04-03 | 2012-04-03 | 2012-04-03 |  | 2012-05-15
| L3 CP - Cooling system produced | 2012-09-06 | 2012-09-06 | 2012-09-06 |  | 2012-09-06
| L3 CP - Start wire bonding sensors | 2012-05-16 | 2012-05-16 | 2012-05-16 |  | 2012-06-28
| L3 CP - Stave production finished | 2012-06-27 | 2012-06-27 | 2012-06-27 |  | 2012-08-09
| L3 CP - Start of layer integration | 2012-11-05 | 2012-11-05 | 2012-11-05 |  | 2012-12-19
| L3 CP - Readout system procured | 2013-02-01 | 2013-02-01 | 2013-02-01 |  | 2013-02-01
| L3 CP - Layer surveyed | 2013-02-01 | 2013-02-01 | 2013-02-01 |  | 2013-03-18
| L3 CP - Cooling system assembled | 2013-10-10 | 2013-10-10 | 2013-10-10 |  | 2013-10-10
| L3 CP - Outside cables installed | 2013-08-26 | 2013-08-26 | 2013-08-26 |  | 2013-08-26
| L3 CP - IST Integrated with HFT | 2013-09-12 | 2013-09-12 | 2013-09-12 |  | 2013-09-12
IGS | L3 - First Article PST Assembled | 2012-02-01 | 2012-02-01 | 2012-02-01
| L3- Insertable Jacket complete | 2012-05-12 | 2012-05-12 | 2012-05-12
| L3 - First Article IDS at BNL | 2011-09-23 | 10/14/11(A) | 2011-09-23 |  | 2011-10-14 | WSC , rest a week later ?
| L3- PXL Platform Design Complete | 2012-01-02 | 2012-01-02 | 2012-01-02
| L3- Lift assembled IDS | 2011-10-15 | 2011-10-15 | 2011-10-15 |  | 2011-10-28
| L3 - First Article IDS Engineering review | 2013-08-01 | 2013-08-01 | 2013-08-01
| L3 - HSSD modification designed | 2013-02-01 | 2013-02-01 | 2013-02-01
SSD
| L3 CP - QRDO Complete | 2011-08-23 17:00 | 7/25/11(A) | 2011-08-23 17:00 | 2011-07-25 | 2011-08-23 | This does not make sense; the design was scheduld for July, so ?
| L3 CP - Ladder Board Prototype Phase I Complete | 2011-10-31 17:00 | 2011-10-31 17:00 | 2011-10-31 17:00 |  | 2011-10-30 | testing is 90% complete. | Revised in BCP# 2
| L3 CP - PCB for Ladder Board Cable Ready for Fabrication | 2011-11-02 17:00 | 2011-11-02 17:00 | 2011-11-02 17:00 |  | 2011-11-02 | Not time critical, has 5 months schedule slack - poorly chosen L3.
| L3 CP - Production DAQ Design Review Completed | 2011-11-28 17:00 | 2011-11-28 17:00 | 2011-11-28 17:00 |  | 2011-11-28
| L3 CP - SSD RDO Design Finished | 2012-01-27 17:00 | 2012-01-27 17:00 | 2012-01-27 17:00 |  | 2012-01-27 |  | Added with BCP #2
| L3 CP - Mechanical Design of SSD components on OSC complete - HFT design Review to sign off | 2012-06-01 08:00 | 2012-06-01 08:00 | 2012-06-01 08:00 |  | 2012-06-29
| L3 CP - Power Supply Design Review Complete | 2012-06-29 17:00 | 2012-06-29 17:00 | 2012-06-29 17:00 |  | 2013-01-30
| L3 CP - Preproduction Ladder Board PCB Received | 2012-08-10 17:00 | 2012-08-10 17:00 | 2012-08-10 17:00 |  | 2012-08-10
| L3 CP - Production Ladder Board Internal Review Completed | 2012-10-08 17:00 | 2012-10-08 17:00 | 2012-10-08 17:00 |  | 2012-10-08
| L3 CP - Production Ladder Board PCB Received | 2013-01-22 17:00 | 2013-01-22 17:00 | 2013-01-22 17:00 |  | 2013-01-22
| L3 CP Slow controls ready for testing | 2013-01-30 17:00 | 2013-01-30 17:00 | 2013-01-30 17:00 |  | 2013-04-01
| L3 CP - Production RDO Board Received | 2013-03-22 17:00 | 2013-03-22 17:00 | 2013-03-22 17:00 |  | 2013-07-09
| L3 CP - Mechanical Components on OSC Installed | 2013-04-01 08:00 | 2013-04-01 08:00 | 2013-04-01 08:00 |  | 2013-06-14
| L3 CP - Electronics Complete | 2013-06-14 17:00 | 2013-06-14 17:00 | 2013-06-14 17:00 |  | 2013-08-16
| L3 CP - Survey Complete | 2013-07-09 17:00 | 2013-07-09 17:00 | 2013-07-09 17:00
| L3 CP - Installation of cooling on STAR platform and Magnet Endcap complete | 2013-08-16 17:00 | 2013-08-16 17:00 | 2013-08-16 17:00
Software
| PXL online software ready for engineering run | 2012-12-04 | 2012-12-04
| PXL online software ready for production run | 2013-10-01 | 2013-10-01
| IST online software for ladder tests | 2013-01-13 | 2013-01-13
| IST online software complete | 2013-07-24 | 2013-07-24
| SSD online software complete | 2013-05-14 | 2013-05-14
| Review of CMM software progress | 2012-04-05 | 2012-04-05
| PXL CMM database delivred for prototype | 2012-11-15 | 2012-11-15
| PXL CMM database delivred for production sectors | 2013-08-22 | 2013-08-22
| IST CMM database delivered | 2013-08-17 | 2013-08-17
| Alignement software Review | 2012-09-20 | 2012-09-20
| Alignment software ready for engineering run | 2013-01-18 | 2013-01-18
Level | Milestone | Planned | Actual /Forecast
PXL
3 | L3 - Production Ladders Ready for Sector Mounting | 2013-02-14 | 2013-02-14
3 | L3 - 1st production sectors ready | 2013-04-15 | 2013-04-15
3 | L3 - Kinematic Mount prototyping complete | 2011-08-15 | 2011-11-30
3 | L3 - Cart Fabrication 1st unit complete | 2012-03-19 | 2012-03-19
3 | L3 - PXL final sensor order | 2012-08-13 | 2012-08-13
3 | L3 - Infrastructure test ladder board readout and analysis complete |  | 6/20/11(A)
3 | L3 - Prototype Kapton/Cu Cable 1st prototype complete | 2012-03-06 | 2012-03-06
3 | L3 - Prototype Kapton/Al Cable 1st prototype complete | 2012-08-01 | 2012-08-01
3 | L3 - Full RDO of ladder (ITB) prototype |  | 6/20/11(A)
3 | L3 - V6 based RDO MB 1st prototype tested | 2012-03-21 | 2012-03-21
3 | L3 - V6 RDO motherboard - 1st production prototype complete | 2012-11-01 | 2012-11-01
3 | L3 - First Production Ladders Ready for Sector Fabrication | 2013-02-13 | 2013-02-13
IST
3 | L3 CP - Prototype flex hybrid produced | 2011-07-12 | 10/8/11(A)
3 | L3 CP - Transition boxes produced and tested | 2012-03-19 | 2012-03-19
3 | L3 CP - Start wire bonding readout chips | 2012-04-04 | 2012-04-04
3 | L3 CP - Sensor procurement finished | 2012-04-03 | 2012-04-03
3 | L3 CP - Start wire bonding sensors | 2012-05-16 | 2012-05-16
3 | L3 CP - Stave production finished | 2012-06-27 | 2012-06-27
3 | L3 CP - Start of layer integration | 2012-11-05 | 2012-11-05
3 | L3 CP - Readout system procured | 2013-02-01 | 2013-02-01
IGS
3 | L3 - First Article PST Assembled | 2012-02-01 | 2012-02-01
3 | L3 - First Article IDS at BNL | 2011-09-23 | 10/14/11(A)
3 | L3- PXL Platform Design Complete | 2012-01-02 | 2012-01-02
3 | L3 - First Article IDS Engineering review | 2013-08-01 | 2013-08-01
3 | L3 - HSSD modification designed | 2013-02-01 | 2013-02-01
Software
| PXL online software ready for engineering run | 2012-12-04 | 2012-12-04
| PXL online software ready for production run | 2013-10-01 | 2013-10-01
| IST online software for ladder tests | 2013-01-13 | 2013-01-13
| IST online software complete | 2013-07-24 | 2013-07-24
| SSD online software complete | 2013-05-14 | 2013-05-14
| Review of CMM software progress | 2012-04-05 | 2012-04-05
| PXL CMM database delivred for prototype | 2012-11-15 | 2012-11-15
| PXL CMM database delivred for production sectors | 2013-08-22 | 2013-08-22
| IST CMM database delivered | 2013-08-17 | 2013-08-17
| Alignement software Review | 2012-09-20 | 2012-09-20
| Alignment software ready for engineering run | 2013-01-18 | 2013-01-18
Formulas:
Actual /Forecast = [Forecast]

## Change Control Thresholds
| DOE-SC-2 | DOE-SC-26 | DOE-BHSO | HFT
| Deputy Director for Science Program | Program Manager | Federal Project Director | Contractor Project Director
| (Level 0) | (Level 1) | (Level 2) | (Level 3)
Scope | Any change affecting Mission Need | Any change affecting CD-4 deliverables | N/A | Any change not affecting CD-4 deliverables
Cost | Any increase in TPC | Any change to TEC or OPC, or cumulative allocation of ≥ $500k contingency | A cumulative increase of ≥ $250k in WBS Level 2 elements, or cumulative allocation of ≥ $250k contingency | Any increase of ≥ $50k in a WBS Level 2 element
Schedule | Any delay in CD-4 date | ≥ 3 months delay of a Level 1 milestone date (other than CD-4), or ≥ 6-month delay of a Level 2 milestone date | ≥ 3-month delay of a Level 2 milestone date | ≥ 1-month delay of a Level 2 milestone date, or ≥ 3-month delay of a Level 3 milestone date

## Baseline Budget
WBS | Description | MIE/Redirect | MIE | BCP 1 | BCP 2 | BCP | BCP | BCP | BCP | BCP | BCP | New BAC
1 | HFT - MIE and Redirect (TEC) | 12788378.06 | 11405442.59 | 19239.25 | 11084.09 | 0 | 0 | 0 | 0 | 0 | 0 | 11435765.93
1.1 | Management | 1926805.96 | 543870.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 543870.5
1.1.1 | Project Management | 1786720.96 | 543870.5 | [8 empty] | 543870.5
1.1.2 | Reviews/Meetings | 0 | [9 empty] | 0
1.1.3 | Funding Milestones | 0 | [9 empty] | 0
1.2 | Pixel Detector (PXL) | 4993451.81 | 4993451.81 | 19239.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5012691.06
1.2.1 | Pixel Mechanics | 1210036.28 | 1210036.28 | [8 empty] | 1210036.28
1.2.2 | Pixel Electronics | 3043067.75 | 3043067.75 | 19239.25 | [7 empty] | 3062307
1.2.3 | Detector Assembly | 225441.7 | 225441.7 | [8 empty] | 225441.7
1.2.4 | Infrastructure | 514906.08 | 514906.08 | [8 empty] | 514906.08
1.3 | Intermediate Silicon Tracker (IST) | 2479590.85 | 2479590.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2479590.85
1.3.1 | Mechanics | 599023.01 | 599023.01 | [8 empty] | 599023.01
1.3.2 | Electronics | 1121755.3 | 1121755.3 | [8 empty] | 1121755.3
1.3.3 | Assembly, testing and installation | 758812.54 | 758812.54 | [8 empty] | 758812.54
1.3.4 | Milestones | 0 | 0 | [8 empty] | 0
1.4 | Silicon Strip Detector (SSD) | 1027393.93 | 1027393.93 | 0 | 11084.09 | 0 | 0 | 0 | 0 | 0 | 0 | 1038478.02
1.4.1 | Mechanics | 0 | 0 | [8 empty] | 0
1.4.2 | Electronics | 730830.44 | 730830.44 |  | -43613.42 | [6 empty] | 687217.02
1.4.3 | Assembly | 40053.81 | 40053.81 |  | -3203.92 | [6 empty] | 36849.89
1.4.4 | Infrastructure | 256509.68 | 256509.68 |  | 57901.43 | [6 empty] | 314411.11
1.5 | Integration and Global Supports (IGS) | 2361135.52 | 2361135.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2361135.5
1.5.1 | Mechanics | 1156752.68 | 1156752.68 | [8 empty] | 1156752.68
1.5.2 | Electronics | 9160.39 | 9160.39 | [8 empty] | 9160.39
1.5.3 | Assembly | 323363.43 | 323363.43 | [8 empty] | 323363.43
1.5.4 | Integration Infrastructure | 308425.41 | 308425.41 | [8 empty] | 308425.41
1.5.5 | Installation | 239228.87 | 239228.87 | [8 empty] | 239228.87
1.5.6 | Integration Engineering Support (post CD-1) | 44387.53 | 44387.53 | [8 empty] | 44387.53
1.5.7 | Integration Engineering Support (post CD-2/3) | 261201.09 | 261201.09 | [8 empty] | 261201.09
1.5.8 | Safety | 18616.1 | 18616.1 | [8 empty] | 18616.1
1.6 | Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6.1 | Online | 0 | 0 | [8 empty] | 0
2 | OPC - R&D Efforts | 300000
| MIE Contingency |  | 3794557.41 | 3775318.16 | 3783473.32 | [6 empty] | 3764234.07
1.1 | Management | 1926805.96
1.1.1 | Project Management | 1926805.96
1.1.1.1 | Actuals through May 2011 | 56457
1.1.1.2 | Labor | 300653.34
1.1.1.3 | Redirected Support | 1242850.46
1.1.1.4 | Materials and Expenses | 326845.16
1.1.1.5 | Schedule Contingency | 0
BCP 1 | Processed 9/1/11 for Ultimate Sensor Change
BCP 2 | Changed sequencing for SSD and added small amount of budget