## Slide 1: Cost and Schedule
Face to Face Meeting – March 2012
Sarah Morgan

## Slide 2: Where we are…
Schedule reworked and approved as of January
  Three baseline changes to date, the last one impacted the entire schedule and a chunk of the costs
LBNL was funded through February 2012
  Working on addendum for balance of year, funds in hand cover us until addendum in place
MIT was funded through March 2012
  Starting work on an addendum for the balance of the year

## Slide 3: Costs at Level 2: Financial Status February
Developed new tools for reporting to DOE
Lvl 2 WBS |  | BAC ($K) | Cum. Actuals | Liens | ETC | EAC | Cum. Plan | Plan vs. Actuals
1.1 | Management | 473 | 122 |  | 351 | 473 | 135 | 13
1.2 | Pixel Detector (PXL) | 4,857 | 1,027 | 94 | 3,735 | 4,857 | 1,255 | 133
1.3 | Intermediate Silicon Tracker (IST) | 2,633 | 344 | 1 | 2,289 | 2,633 | 443 | 98
1.4 | Silicon Strip Detector (SSD) | 1,022 | 40 | 95 | 888 | 1,022 | 179 | 45
1.5 | Integration and Global Supports (IGS) | 2,757 | 961 | 54 | 1,743 | 2,757 | 1,048 | 33
1.6 | Software |  |  |  |  |  |  | 
1.7 | Redirected | 1,187 | 385 |  | 802 | 1,187 | 409 | 23
 | Subtotal | 12,929 | 2,879 | 244 | 9,806 | 12,929 | 3,468 | 346
 | MIE/Contingency | 3,514 | 27% |  |  | 3,514 | 27% | 
 | HFT - MIE and Redirect | 16,443 | 2,879 | 244 | 9,806 | 16,443 | 3,468 | 346
2 | OPC - R&D Efforts | 300 | 299 |  | 1 | 300 | 300 | 1
HFT Total Project Costs |  | 16,743 | 3,178 | 244 | 9,807 | 16,743 | 3,768 | 346

## Slide 4: Plan vs Actuals and Funding
Chart: $K
| Prior | Oct-11 | Nov-11 | Dec-11 | Jan-12 | Feb-12 | Mar-12 | Apr-12 | May-12 | Jun-12 | Jul-12 | Aug-12 | Sep-12 | FY12
Actual | 1376505.8 | 1548240.8 | 1847573.8 | 2217821.8 | 2330404.8 | 2493724.8 | 2493724.8 | 2493724.8 | 2493724.8 | 2493724.8 | 2493724.8 | 2493724.8 | 2493724.8 | 2493724.8
Plan | 2501865.07 | 2951412.08 | 3300709.56 | 3793161 | 2724013.11 | 3059840.49 | 3447521.71 | 4278371.59 | 5019969.13 | 5560241.87 | 6125932.01 | 6995663.8 | 7457524.33 | 7457524.33
Funding | 6800000 | 7265442.2 | 7730884.4 | 8196326.6 | 8661768.8 | 9127211 | 9127211 | 9127211 | 9127211 | 9127211 | 9127211 | 9127211 | 9850000 | 9850000

## Slide 5: Variances as of February
Cost:
  1.2 Pixel Detector – outstanding liens
  1.3 IST – delays in placing silicon order
  1.4 SSD – Slow start with French contract
  1.5 IGS – outstanding liens
Schedule:
  Milestones have been analyzed and the baseline has been updated to address major changes.

## Slide 6: Cost Baseline Documentation
WBS | Description | MIE/Redirect | MIE | BCP 1 | BCP 2 | BCP 3 | New BAC
1 | HFT - MIE and Redirect (TEC) | $12,788,378 | $11,545,528 | $19,239 | $11,084 | $109,944 | $12,928,645
1.1 | Management | $1,926,806 | $683,956 | $- | $- | $(1,454,188) | $472,618
1.2 | Pixel Detector (PXL) | $4,993,452 | $4,993,452 | $19,239 | $- | $(156,301) | $4,856,390
1.3 | Intermediate Silicon Tracker (IST) | $2,479,591 | $2,479,591 | $- | $- | $153,474 | $2,633,065
1.4 | Silicon Strip Detector (SSD) | $1,027,394 | $1,027,394 | $- | $11,084 | $(16,156) | $1,022,322
1.5 | Integration and Global Supports (IGS) | $2,361,136 | $2,361,136 | $- | $- | $396,264 | $2,757,400
1.6 | Software | $- | $- | $- | $- | $- | $-
1.7 | Redirected Support | $- | $- | $- | $- | $1,186,850 | $1,186,850
2 | OPC - R&D Efforts | $300,000 | $- | $- | $- | $- | 
 | MIE Contingency |  | $3,654,472 | $3,635,233 | $3,624,149 | $3,514,206 | $3,514,206
BCP 1 | Processed 9/1/11 for Ultimate Sensor Change |  |  |  |  |  | 
BCP 2 | Changed sequencing for SSD and added small amount of budget |  |  |  |  |  | 
BCP 3 | Updated schedule to reflect current ETC |  |  |  |  |  | 

## Slide 7: Change Control Thresholds
 | DOE-SC-2 | DOE-SC-26 | DOE-BHSO | HFT
 | Deputy Director for Science Program | Program Manager | Federal Project Director | Contractor Project Director
 | (Level 0) | (Level 1) | (Level 2) | (Level 3)
Scope | Any change affecting Mission Need | Any change affecting CD-4 deliverables | N/A | Any change not affecting CD-4 deliverables
Cost | Any increase in TPC | Any change to TEC or OPC, or cumulative allocation of ≥ $500k contingency | A cumulative increase of ≥ $250k in WBS Level 2 elements, or cumulative allocation of ≥ $250k contingency | Any increase of ≥ $50k in a WBS Level 2 element
Schedule | Any delay in CD-4 date | ≥ 3 months delay of a Level 1 milestone date (other than CD-4), or ≥ 6-month delay of a Level 2 milestone date | ≥ 3-month delay of a Level 2 milestone date | ≥ 1-month delay of a Level 2 milestone date, or ≥ 3-month delay of a Level 3 milestone date
We are now above the cumulative cost increase threshold.

## Slide 8: Changes to Lvl 2 Milestones
Level | Milestone | PEP Date | BCP #3 Date | Forecast
1 | CD-0 Approve Mission Need | Q2, FY09 (A) | Feb-09 (A) | 
1 | CD-1 Approve Alternative Selection and Cost Range | Q4, FY10 (A) | Aug-10 (A) | 
1 | CD-2 Approve Performance Baseline | Q4FY11 | Oct-11 (A) | 
1 | CD-3 Approve Start of Fabrication | Q4FY11 | Oct-11 (A) | 
1 | CD-4 Approve Project Completion | Q3FY15 | Jul-15 | 7/30/15
2 | PXL Prototype Sector Design Complete | Q1FY11(A) | Dec-10 (A) | 
2 | PXL Receive Prototype sensors from IPHC | Q2FY11(A) | Mar-11 (A) | 
2 | PXL Prototype PXL Insertion mechanism Testing Complete | Q1FY12 | Dec-11 (A) | 
2 | PXL Final PXL Sensors received | Q1FY13 | Oct-12 | 10/16/12
2 | PXL Production Sector Assembly Start | Q2FY13 | Feb-13 | 2/15/13
2 | PXL detector available for insertion | Q1FY14 | Jun-13 | 6/25/13
2 | IST Sensor design finished | Q1FY12(A) | Jul-11 (A) | 
2 | IST Prototype ladder tested | Q2FY12 | Mar-12 | 3/30/12
2 | IST Flex hybrid produced | Q3FY12 | Jun-12 | 6/4/12
2 | IST First staves produced | Q4FY12 | Sep-12 | 10/17/12
2 | IST Staves finalized | Q2FY13 | Mar-13 | 3/7/13
2 | IST assembled onto MSC | Q4FY13 | May-13 | 5/23/13
2 | SSD Prototype Ladder Board design finished | Q1FY11(A) | Oct-10 (A) | 
2 | SSD QRDO Board design finished | Q1FY12 | Jul-11 (A) | 
2 | SSD Preproduction Design Review of RDO | Q3FY12 | Jun-12 | 9/4/12
2 | SSD Production of Ladder Boards ready to begin | Q1FY13 | Nov-12 | 11/6/12
2 | SSD Assembled onto OSC ready for installation | Q1FY14 | Aug-13 | 8/28/13
2 | IGS Final MSC assembled at BNL | Q2FY13 | Nov-12 | 11/5/12
2 | IGS Final OSC at BNL | Q4FY13 | May-13 | 5/19/13
2 | IGS HFT assembled and integrated into STAR | Q1FY15 | Nov-13 | 11/20/13

## Slide 9: Changes to Lvl 3 Milestones
L3 EF milestone |  | EF date | BCP #3
PXL | L3 - sector laminates ordered | 9/9/11 | 8/6/12
 | L3 - Production Ladders Ready for Sector Mounting | 2/14/13 | 2/14/13
 | L3 - 1st production sectors ready | 4/15/13 | 4/15/13
 | L3 - Insertion Test bed complete | 6/27/11 | 11/16/11 (A)
 | L3 - Kinematic Mount prototyping complete | 8/15/11 | 11/20/11 (A)
 | L3 - Cart Fabrication 1st unit complete | 3/19/12 | 6/18/12
 | L3 - Patch Panel Bulkhead 1st unit complete | 4/18/12 | 7/19/12
 | L3 - PXL final sensor order | 8/13/12 | 8/13/12
 | L3 - Infrastructure test ladder board readout and analysis complete |  | 6/20/11(A)
 | L3 - Prototype Kapton/Cu Cable 1st prototype complete | 3/6/12 | 6/25/12
 | L3 - Prototype Kapton/Al Cable 1st prototype complete | 8/1/12 | 9/5/12
 | L3 - Full RDO of ladder (ITB) prototype |  | 6/20/11(A)
 | L3 - V6 based RDO MB 1st prototype tested | 3/21/12 | 3/21/12
 | L3 - V6 RDO motherboard - 1st production prototype complete | 11/1/12 | 11/1/12
 | L3 - First Production Ladders Ready for Sector Fabrication | 2/13/13 | 2/13/13
 | L3 - Deliver 2nd Detector + Spare Ladders | 9/27/13 | 9/27/13

## Slide 10
L3 EF milestone |  | EF date | BCP #3
IST | L3 CP - Prototype flex hybrid produced | 7/12/11 | 10/8/11(A)
 | L3 CP - Prototype sensors produced | 10/30/11 | 12/15/11 (A)
 | L3 CP - Support structure produced | 1/25/12 | 12/11/12
 | L3 CP - Prototype Transition boxes produced and tested | 3/29/12 | 5/17/12
 | L3 CP - Start wire bonding readout chips | 5/16/12 | 7/11/12
 | L3 CP - Sensor procurement finished | 5/15/12 | 7/14/12
 | L3 CP - Cooling system produced | 9/6/12 | 9/6/12
 | L3 CP - Start wire bonding sensors | 6/28/12 | 9/6/12
 | L3 CP - Stave production finished | 8/9/12 | 10/10/12
 | L3 CP - Start of layer integration | 12/19/12 | 3/8/13
 | L3 CP - Readout system procured | 2/1/13 | 2/1/13
 | L3 CP - Layer surveyed | 3/18/13 | 5/23/13
 | L3 CP - Cooling system assembled | 10/10/13 | 10/10/13
 | L3 CP - Outside cables installed | 8/26/13 | 8/26/13
 | L3 CP - IST Integrated with HFT | 9/12/13 | 9/12/13
IGS | L3 - First Article PST Assembled | 2/1/12 | 6/22/12
 | L3- Insertable Jacket complete | 5/12/12 | 5/12/12
 | L3 - First Article IDS at BNL | 9/23/11 | 10/14/11(A)
 | L3- PXL Platform Design Complete | 1/2/12 | 2/23/12
 | L3- Lift assembled IDS | 10/15/11 | 11/2/11(A)
 | L3 - First Article IDS Engineering review | 8/1/13 | 8/1/13
 | L3 - HSSD modification designed | 2/1/13 | 2/1/13

## Slide 11
L3 EF milestone |  | EF date | BCP #3
SSD |  |  | 
 | L3 CP - QRDO Complete | 8/23/11 | 7/25/11(A)
 | L3 CP - Ladder Board Prototype Phase I Complete | 10/31/11 | 10/31/11(A)
 | L3 CP - PCB for Ladder Board Cable Ready for Fabrication | 11/2/11 | 4/3/12
 | L3 CP - Production DAQ Design Review Completed | 11/28/11 | 11/28/11 (A)
 | L3 CP - SSD RDO Design Finished | 1/27/12 | 3/30/12
 | L3 CP - Mechanical Design of SSD components on OSC complete - HFT design Review to sign off | 6/1/12 | 6/1/12
 | L3 CP - Power Supply Design Review Complete | 6/29/12 | 6/29/12
 | L3 CP - Preproduction Ladder Board PCB Received | 8/10/12 | 8/10/12
 | L3 CP - Production Ladder Board Internal Review Completed | 10/8/12 | 10/8/12
 | L3 CP - Production Ladder Board PCB Received | 1/22/13 | 1/22/13
 | L3 CP Slow controls ready for testing | 1/30/13 | 4/3/13
 | L3 CP - Production RDO Board Received | 3/22/13 | 5/13/13
 | L3 CP - Mechanical Components on OSC Installed | 4/1/13 | 4/1/13
 | L3 CP - Electronics Complete | 6/14/13 | 7/25/13
 | L3 CP - Survey Complete | 7/9/13 | 7/9/13
 | L3 CP - Installation of cooling on STAR platform and Magnet Endcap complete | 8/16/13 | 8/16/13
Software |  |  | 
 | PXL online software ready for engineering run | 12/4/12 | 12/4/12
 | PXL online software ready for production run | 10/1/13 | 10/1/13
 | IST online software for ladder tests | 1/13/13 | 1/13/13
 | IST online software complete | 7/24/13 | 7/24/13
 | SSD online software complete | 5/14/13 | 5/14/13
 | Review of CMM software progress | 4/5/12 | 4/5/12
 | PXL CMM database delivred for prototype | 11/15/12 | 11/15/12
 | PXL CMM database delivred for production sectors | 8/22/13 | 8/22/13
 | IST CMM database delivered | 8/17/13 | 8/17/13
 | Alignement software Review | 9/20/12 | 9/20/12
 | Alignment software ready for engineering run | 1/18/13 | 1/18/13

## Slide 12: Report on Milestones
L3 – Prototype Kapton/Cu Cable 1st prototype complete
  This task is delayed by 3.5 months in the schedule due to several factors. The first is that the incorporation of the ultimate sensors into the prototype detector had led to more development (hardware and firmware) time needed for probe testing. The second is that, due to availability of collaborators to work in Berkeley, we made a push on the RDO firmware and hardware and are now correspondingly ahead in those tasks. I believe that perhaps half of the delay in the full task chain that leads to a complete and tested ladder hybrid cable design can be made up in the next set of tasks.
L3 – Cart Fabrication 1st unit complete
  This item is not on the critical path and will be moved such that it can be produced when resources are more readily available (sometime after the main push for the IDS installation in the summer). This is not a high complexity item.
L3 – Prototype Kapton/Al Cable 1st prototype complete
  This task is tied to the first "L3 - Prototype Kapton/Cu Cable 1st prototype complete" from above. It will slip correspondingly in the schedule. But not as much, I believe, as the schedule will indicate. I am already preparing the layout for the cable on the assumption that the prototype cable testing will be successful.
L3 - First Article PST Assembled
  In the MSC prod the PIT was lost before base lining. This adds about 3 months. The remaining delay is due to CN60 material delivery issues as discussed in last months report.
L3 milestones for IST
  All of these delays, which are coupled, are due to a) 4 month delay in fabrication of Sensors, b) failures in initial hybrid cables by manufacturer (2 mo.) and a need to extend testing period to ensure nesc. cable modification are understood before placement of production orders. As mentioned part of the delay for EF is picked up by slack in the previous schedule, and the lessons learned from the assembly of prototype may allow to pick up additional time in the production assembly.
L3- PXL Platform Design Complete
  The preliminary design is complete and quotes have been requested. Signoff is expected with a few weeks and should be done by 3/30/12.
L3- SSD Completion of RDO Design
  This was scheduled for January 27. This will likely be completed in March, effort are well underway.

## Slide 13: Outstanding Schedule Concerns
We continue to need to pay close attention to impacts to our early finish schedule
  Would like to better understand SSD’s schedule after progress can be assessed with the French
  Need to better understand the assembly path through IST
  As the budget becomes clearer, there may be impacts to the RHIC running schedule
    Will need to do analysis as this develops to understand the impacts

## Slide 14: Draft LBNL Addendum Info
LBNL Activities |  | Current MPO/IWO Ceiling | Amendment #3 | Revised MPO/IWO
1.1 | Project Management | 623,340 | 50,499 | 673,839
1.2 | Pixel Detector (PXL) | 1,459,910 | 1,318,744 | 2,778,654
1.2.1 | PXL Mechanical Work | 502,783 | 362,586 | 865,368
1.2.2 | PXL Electronics Work | 801,509 | 777,648 | 1,579,157
1.2.3 | Detector Assembly | 42,298 | 13,202 | 55,500
1.2.4 | Infrastructure | 113,320 | 165,309 | 278,629
1.3 | IST | 36,324 | 307,486 | 343,810
1.3.1 | Mechanics | 36,324 | 307,486 | 343,810
1.4 | SSD | 28,422 | 165,897 | 194,319
1.4.2 | Electronics |  | 81,153 | 81,153
1.4.3 | Assembly | - | - | -
1.4.4 | Infrastructure | 28,422 | 84,744 | 113,166
1.5 | Integration | 750,267 | 513,762 | 1,264,029
1.5.1 | Mechanics | 500,671 | 306,580 | 807,251
1.5.3 | Assembly | 19,369 | 38,031 | 57,401
1.5.4 |  |  | 11,394 | 
1.5.5 | Installation | 12,919 | 7,765 | 20,685
1.5.6 | Integration Engineering Support (post CD-1) | 177,442 | - | 177,442
1.5.7 | Integration Engineering Support (post CD-2/3) | 39,866 | 149,992 | 189,858
1.6 | Software | - | - | -
1.7 | Redirect Support | - | - | -
 |  | 2,898,263 | 2,356,389 | 5,254,652

## Slide 15: LBNL Next Steps
Concurrence on Budget
Concurrence on activities for the balance of the year (that hopefully ties directly to above mentioned budget)
Submit to contract offices… and let process for three months

## Slide 16: Draft Addendum for MIT
Have started looking at balance of this years predicted expenses
Will have a draft for Flemming and Gerrit to review by Friday
Will then work with the institutions to encourage a more speedy than last time effort