## Slide 1: PXL Mechanical 14-March-2012
HFT face to face

## Slide 3: Critical items/tasks for run-13 installation
3 or more working sectors
spatial map of PXLs in working sectors
7 dummy sectors for air flow
complete insertion carriage
build second insertion carriage
complete detector/transfer box
build second detector/transfer box
design and build cart for detector/transfer box
design and build cabling plant for two PXL halves
design and build bulk heads with attachments and seals
cooling plant

## Slide 4: Critical items/tasks for run-13 installation
3 or more working sectors
  Design cable connection
  Design tooling ball location and fixation
  CF tech fabrication time
spatial map of PXLs in working sectors
  OGP rotary head delivery delayed, March 30
  Need dummy sector with thinned silicon to develop procedures
    requires ladder assembly fixture modifications – waiting for main LBL shop – but should have parts end of this week then CF techs can finish sector fab by March 30
  sector support – waiting for main LBL shop
7 dummy sectors for air flow
  can strip cooling test sectors?

## Slide 5: Critical items/tasks for run-13 installation
complete insertion carriage
  modify release mechanism
build second insertion carriage
  order second copies of machined parts – 10s k$ - long lead time?
  some CF tech fabrication time
complete detector/transfer box
  strengthen cover
  order/fab cover plates
  CF tech time
build second detector/transfer box
  CF tech time

## Slide 6: Critical items/tasks for run-13 installation
design and build cart for detector/transfer box
  BNL design and fabricate?
design and build cabling plant for two PXL halves
  design ladder flex cables with connectors
  design low mass cables with support structures and take up structures
  design high mass cables with support structures – coupling arm
  status - design in process, but awaiting models
  build – CF tech time
(place holders)

## Slide 7: Critical items/tasks for run-13 installation
design and build bulk heads with attachments and seals
  design feed through cards and connector structures
  design fastening system to PIT/MSC
  design sealing system to PIT/MSC
(place holder)

## Slide 8: Critical items/tasks for run-13 installation
cooling plant
  design
    size chiller
    design heater and feed back control
    size and order pump
    size and order filter
    design and fab housing
    design and fab ducting
    order ducting internal to MSC
    determine plant location
  latest news (yesterday) Dana has found a vendor that may be able to do the job, but meeting time constraint of summer installation is very tight.

## Slide 9: Critical items/tasks for run-14 installation
10 or more working sectors
spatial map of PXLs in working sectors

## Slide 10: Misc. Mechanical run-13 Critical items/tasks
MSC hardware
BBC support
External adjustable beam pipe support