## Slide 1: HFT Software Status
S. Margetis, KSU
OPA review, July 17, 2012, BNL
StPixelFastSimMaker/
StEvent containing PIXEL and IST Hits hits
GEANT
StiPixel
StiIst
Hit reconstruction
Tracking
StEvent containing tracks
with PIXEL and IST Hits hits
StIstFastSimMaker/
StDaqMaker
StDaqLib
StPixelDaqMaker
StPixelRecoMaker
StIstRecoMaker
DATA STREAM
SIMULATION STREAM

## Slide 2: Outline
Brief overview of subsystem
Technical Progress since last review
Construction Plans
Outstanding technical issues and plans
Schedule & Cost
  Cost to date and projection (from Sarah)
Resources
  People, institutions and
Risk assessment; value engineering
Summary

## Slide 3: Overview of subsystem
WBS 1.6 (Software) is the sum of Online and Offline software tasks
The Online software is a sub-detector deliverable and contains Slow controls, online monitoring etc
The Offline software is responsible for the event reconstruction, starting from raw data all the way to particle quantities. It includes tasks like alignment, hit/track/vertex finding etc
WBS 1.6 is divided into two parts. Part one (on-scope) contains all the essential tasks for the successful operation of the detector (calibrations etc). Part two contains the remaining tasks.
Subsystem meets weekly to plan work and get updates. Participates in weekly TC meetings as well.
Subsystem is an integral part of STAR’s S&C environment, interacting very closely with it on a regular basis.

## Slide 4
General Flowchart of Software Tasks
Offline/Online
* VMC, STV, CA ready
Geometry
Calibrate
Read (Make) Raw Data
DSTs
All Detectors
Done
N
Y
Hits/Tracks/Vertices*
ForEachDataSet
SIMULATION STREAM
DATA STREAM
Analysis
All Detectors
Slow controls
Diagnostics/Errors/Actions
Monitoring/Fast Online
State Db
Run Interface

## Slide 5
Brief overview of subsystem
Technical Progress since last review
Construction Plans
Outstanding technical issues and plans
Schedule & Cost
  Cost to date and projection (from Sarah)
Resources
  People, institutions and
Risk assessment; value engineering
Summary

## Slide 6: Areas of activities since CD2/3 (a year ago)
  HFT Geometry model
  HFT Survey & Alignment related work
  Slow/Fast PXL response simulation
  Prototype (BUR) simulations/tracking
  Offline structures (Hits etc)
  Simulation environment (UPC e- background, Pileup)
  Conventions (naming scheme defined), Db
  ----------------------------------------------------------------
  Hit/Event vertex finders/Kalman fitter for decays
  Evaluation/Analysis framework
  Tests of new STV tracker, VMC environment
  ‘Online’ data format/slow controls/online QA/Db considerations
RED = On-scope activity

## Slide 7
HFT Geometry model update
  Creating the Y2013/14 geometry in AgML based on Solid-Works Models
  We had an internal review in March, working on recommendations etc
  Work on SSD/IST in progress
  Work on details of support structures etc in progress
  Manpower probably O.K. but we seek more help

## Slide 8: PXL sector modeling in GEANT - detailed work on structure and thickness (shape and material) - optimization in progress

## Slide 9: IDS modeling

## Slide 10: MSC modeling

## Slide 11
HFT Survey work
  PXL+SSD work has already begun, IST is setting up
    Single chip and 3-chip ladder done. Full PXL sector (photo) in progress
    SSD ladder preliminary survey done, parameter space defined
    IST preliminary work on prototype ladder about to begin at BNL
  We had an internal review on procedures/general scheme in May
  A lot of detailed work in front of us, but expertise is building up
  Manpower issues addressed (most) but there are tasks available

## Slide 12: Sensor’s features for individual pixel coordinates identified - Need be programmable for automating process

## Slide 13
SSD ladder survey

## Slide 14
Slow/Fast PXL response simulation
  Most work done by IPHC (Strasburg) Collaborators
  The have developed a Root program, DIGMAPS, for response studies
  Analyzed CERN test-beam data with our sensors to fix parameters
  We are about to get their tune to use for our studies and compare with default “geometrical mean” approach. Then, build fast simulator with appropriate errors
  SSD simulators exist, IST is relatively simple, but still not there yet
  These are low priority tasks but need to start

## Slide 15
Tracking (Physics?) with TPC+PXL prototype ?
  BUR simulations done, presented and used as input
  Simulations show (see next slide too) that there might some physics opportunities
  This connects to the bigger issue of Tracking and whether inside-out tracking is possible. Is CA useful? Work in this direction is scheduled
  This is vital work for the project. ANY help and idea is invaluable.

## Slide 16: BUR results based on full simulations
500 M AuAu mbias events

## Slide 17
Offline chain - Update
Establishing a working offline chain
Modify structures/makers to our needs
Closely tied to S&C territory !
Need to stay informed and implement new strategies (e.g. no minimc etc)
We ‘ve gone through initial loops but not done yet(see 2 slides)
Expert help invaluable
StEvent
StRndHitCollection
StRndHit
StEvent
StHftHitCollection
StHftHit
Actual structures
Proposed structures

## Slide 18
Numbering convention/Configuration of detector elements
  We have defined and documented the scheme for all HFT elements
  Complies with STAR conventions
  IST example is shown below
http://drupal.star.bnl.gov/STAR/event/2012/03/09/hft-software/hft-numbering-schemedoc-10

## Slide 19: Miscellaneous
  Simulation environment (UPC e- background, Pileup mechanism)
    We did improve our understanding and way of generating this
    We still need to put all this to work with STAR’s official pileup scheme
  Event vertex finders
    Important evaluation work goes on now
  Web Docs
    Jonathan and I are organizing better our Off-Drupal personal doc areas
    S&C provided an AFS area for Off-Drupal (really public) access
    Drupal pages need rework from scratch

## Slide 20
Brief overview of subsystem
Technical Progress since last review
Construction Plans
Outstanding technical issues and plans
Schedule & Cost
  Cost to date and projection (from Sarah)
Resources
  People, institutions and
Risk assessment; value engineering
Summary

## Slide 21: Planned work to do
  Besides things I have already mentioned above
  Raw data un-packers/Cluster-Hit finders
  Tests of CA/new STV tracker, VMC environment
  ‘Online’ data format/slow controls/online QA/Db considerations
  With the prototype PXL installation and the new institutional involvement the Collaboration will refocus some of its effort to the new device.

## Slide 22
Brief overview of subsystem
Technical Progress since last review
Construction Plans
Outstanding technical issues and plans
Schedule & Cost
  Cost to date and projection (from Sarah)
Resources
  People, institutions and
Risk assessment; value engineering
Summary

## Slide 23: Schedule/Milestones
NOW
10/2012
Most immediate activities are in the areas of Online, Calibrations and Offline software

## Slide 24
LEVEL-3 Milestones
Survey/Alignment/Db/Online are immediate on-project activities
Geometry/Offline/Analysis are hidden but essential tasks

## Slide 25
Brief overview of subsystem
Technical Progress since last review
Construction Plans
Outstanding technical issues and plans
Schedule & Cost
  Cost to date and projection (from Sarah)
Resources
  People, institutions and
Risk assessment; value engineering
Summary

## Slide 26: Task Overview and FTE needs
List is for Offline tasks only
Following FTE estimate does not include BNL- core group contributed effort in tracking/vertexing/calibrations etc. Also, numbers are on the under-estimate side
It comes down to about 4 FTE/year for ~two years
  We have about half of that
  The rest will come as we near the hardware completion, the prototype development and institutional manpower redirection

## Slide 27
NEEDS
UPDATE
X
UIC
X

## Slide 28
Brief overview of subsystem
Technical Progress since last review
Construction Plans
Outstanding technical issues and plans
Schedule & Cost
  Cost to date and projection (from Sarah)
Resources
  People, institutions and
Risk assessment; value engineering
Summary

## Slide 29
Software Risks (rather Challenges) are related to:
  People: (in)sufficient manpower for tasks
    We are addressing this by prioritizing tasks and management actions
  Overall environment functionality (tracking etc)
    We engage in discussions with STAR S&C management for overall timeline development/understanding
  Our value engineering is to use field-proven techniques

## Slide 30: Summary
  …